## 1_PROGRESS PAYMENT
Subcontract Payment Request | [5 empty] | SIGN | IN CHARGE | CONS DEPT. | PLN DEPT. | P.M
[7 empty] | / / | / / | / / | / /
INVOICE DATE |  |  | INVOICE NO |  |  |  | DUE DATE |  |  | ADMIN DEPT.
PROJECT | HL-GA Battery Project |  |  | CONTRACT NUMBER
SUBCONTRACTOR | Nahshon MEP |  |  | CONTRACT PRICE |  | 1789000
SCOPE OF WORKS | Additional Finish Works PKG-7 |  |  | P/BOND AMT/EXPIRY | [5 empty] | FNC DEPT.
CONTRACT PERIOD | 2026.08 ~ 2026.11 | CONTRACT DATE |  | AP-BOND AMT/EXPIRY
INSURANCE |  |  |  | W-BOND AMT/EXPIRY
( Currency : USD )
DESCRIPTION |  |  | UP TO PREVIOUS BILL | THIS BILL | UP TO THIS BILL |  |  | REMARKS
PAYMENT RECEIVED IN ADVANCE |  | ① | 0 | 357800 | 357800 |  |  | 20%
WORKS DONE | WORK DONE |  | 0 | 218000 | 218000 |  |  | 12.19%
| V/O, C/O |  | 0 | 0 | 0
| OTHERS |  | 0 | 0 | 0
| GROSS AMOUNT | ② | 0 | 218000 | 218000 | 0 | 0
ADV. REPAYMENT | GROSS AMOUNT | ③ | 0 | 0 | 0
RETENTION | 5% | ④ | 0 | 10900 | 10900
CONTRA CHARGES | MATERIALS |  | 0 | 0 | 0
| LABOUR CHG |  | 0 | 0 | 0
| EQUIPMENT |  | 0 | 0 | 0
| OTHERS |  | 0 | 0 | 0
| SUB-TOTAL | ⑤ | 0 | 0 | 0
NET AMOUNT |  | ⑥=①+②-③-④-⑤ | 0 | 564900 | 564900
TAXES |  | ⑦ | 0 | 0 | 0
| WITHHOLDING (less) | ⑧ | 0 | 0 | 0
NET RECEIPT |  | ⑨=⑥+⑦-⑧ | 0 | 564900 | 564900
ADDITIONAL INPUTS (not printed on payment request)
Application no. |  |  |  | Period to
Contractor address
CCI job no.
Previous retainage
Previous retainage: leave blank to calculate from the current retainage rate; enter the approved prior amount to override.
Progress %: enter previous cumulative in sheet 3 Q2, current cumulative in S2. Retainage %: C25 above.
Note on I6: 결재순서 담당 > 담당팀장 > 공무팀장 > 관리팀장 > 현장소장
Note on C10: 매달 25일 고정(수정)
Note on F10: 맨 뒤에 숫자만 강제 수정(기성청구 회차) 1회차 > 1 3회차 > 3
Note on J10: 고정임(익월 말)

## 2_APPLICATION
APPLICATION AND CERTIFICATE FOR PAYMENT
TO GC |  |  |  | PROJECT: | HL-GA Battery Project |  | APPLICATION #:
PERIOD TO:
CCI JOB #:
CONTRACT NO:
APPLICATION DATE:
FROM CONTRACTOR: |  | Nahshon MEP |  |  |  |  | INVOICE #:
CONTRACTOR'S APPLICATION FOR PAYMENT |  |  |  |  | The undersigned Contractor certifies that to the best of the Contractor's knowledge,
Application is made for payment, as shown below, in connection with the Contract. |  |  |  |  | information and belief the Work covered by this Application for Payment has been
completed in accordance with the Contract Documents, that all amounts have been
1 | ORIGINAL CONTRACT SUM............................ |  |  | 1789000 | paid by the Contractor for Work for which previous Certificates for Payment were issued
and payments received from the Owner, and that current payment shown herein is now due.
2 | NET CHANGE BY CHANGE ORDERS............. |  |  | 0
[5 empty] | Contractor: | Nahshon MEP
3 | CONTRACT SUM TO DATE (LINE 1 & 2)......... |  |  | 1789000
[5 empty] | By: |  |  | Date:
4 | TOTAL COMPLETED & STORED TO DATE.... |  |  | 218000 | General Manager
State of:
5 | RETAINAGE: |  |  |  | County of:
Subscribed and sworn to before
| RETAINAGE ON COMPLETED WORK |  | 10900 |  | me this day of
| OTHER NET DEDUCTIONS / ADDITIONS |  | -357800 |  | Notary Public:
My Commission expires:
| TOTAL NET DEDUCTIONS |  |  | -346900
6 | TOTAL EARNED LESS NET DEDUCTIONS |  |  | 564900 | CERTIFICATE FOR PAYMENT
(LINE 4 LESS LINE 5 TOTAL)
In accordance with the Contract Documents, based on on-site observations and the data comprising
7 | LESS PREVIOUS APPLICATIONS FOR PAYMENT |  |  | 0 | this application, the General Contractor certifies to the Owner that to the best of its knowledge,
| (LINE 6 FROM PRIOR CERTIFICATE) |  |  |  | information and belief the work has progressed as indicated, the quality of the work is in accordance
with the Contract Documents, and the Contractor is entitled to payment of the AMOUNT CERTIFIED.
8 | CURRENT PAYMENT DUE......................................... |  |  | 564900
[5 empty] | AMOUNT CERTIFIED................................................................................................... |  |  |  | 564900
9 | BALANCE TO FINISH, INCLUDING RETAINAGE |  |  |  | (Attached explanation if amount certified differs from the amount applied for. Initial all figures on this
| (LINE 3 LESS LINE 6) |  | 1224100 |  | Application and on the continuation sheet that are changed to conform to the amount certified.)
GENERAL CONTRACTOR
[5 empty] | By: |  |  | Date:
This certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the Contractor named
herein. Issuance, payment and acceptance of payment are without prejudice to any rights of the Owner
of Contractor under this Contract.

## 3_CONTINUATION SHEET
CONTINUATION SHEET
[19 empty] | APPLICATION NO: | 1
| APPLICATION AND CERTIFICATE FOR PAYMENT, | [17 empty] | APPLICATION DATE: | 2026-09-20
| Containing Contractor's signed Certification, is attached. | [17 empty] | PERIOD TO: | 09/01/26 ~ 09/30/26 (Forecast)
In tabulations below, amounts are stated to the nearest dollar..
Use column I on Contracts where variable retainage for line items may apply.
| A | B |  |  | C | [5 empty] | D |  | E |  | F |  |  | G |  | H
| ITEM NO. | DESCRIPTION OF WORK | Specification | Unit | CONTRACT VALUE (계약) | [5 empty] | WORK COMPLETED |  |  |  | UP TO THIS BILL |  | % | BALANCE TO |  | RETAINAGE
[11 empty] | PREVIOUS |  | THIS PERIOD
[5 empty] | Quantity | Material | Labor | Expense | Unit Price | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  | Quantity | Amount
| 1 | 건축공사 |  | L/S | 1 |  |  |  |  | 744998.1 |  | 0 | 0 | 132127.08 | 0 | 132127.08 | 17.74% |  | 339684.89
|  | 1) TEMPORARY |  | L/S | 1 |  |  |  |  | 37554 |  | 0 |  | 0 |  | 0 | 0% |  | 37554
|  | 2) DOOR, WINDOW |  | L/S | 1 |  |  |  |  | 25683.44 |  | 0 |  | 0 |  | 0 | 0% |  | 25683.44
|  | 3) DRYWALL |  | L/S | 1 |  |  |  |  | 94548.52 |  | 0 |  | 43909.46 |  | 43909.46 | 46.44% |  | 50639.06
|  | 4) WALL FINISH |  | L/S | 1 |  |  |  |  | 83277.19 |  | 0 |  | 0 |  | 0 | 0% |  | 83277.19
|  | 5) FLOOR FINISH |  | L/S | 1 |  |  |  |  | 67623.82 |  | 0 |  | 1859.6 |  | 1859.6 | 2.75% |  | 65764.22
|  | 6) CEILING FINISH |  | L/S | 1 |  |  |  |  | 45294 |  | 0 |  | 0 |  | 0 | 0% |  | 45294
|  | 7) MISCELLANEOUS |  | L/S | 1 |  |  |  |  | 193390.14 |  | 0 |  | 52972.812 |  | 52972.812 | 27.39% |  | 16664.34
|  | 8) TOLIET WORKS |  | L/S | 1 |  |  |  |  | 31845.22 |  | 0 |  | 0 |  | 0 | 0% |  | 4751.72
|  | 9) CIVIL WORKS |  | L/S | 1 |  |  |  |  | 165781.77 |  | 0 |  | 33385.211 |  | 33385.211 | 20.14% |  | 10056.92
| 1.1 | 설비공사 |  | L/S | 1 |  |  |  |  | 571271.38 |  | 0 | 0 | 17851.5 | 0 | 17851.5 | 3.125% |  | 553419.87
|  | M0 General | 74 | L/S | 1 |  |  |  |  | 44319.55 |  | 0 |  | 0 |  | 0 | 0% |  | 44319.55
|  | M1-1. Equipment | 74 | L/S | 1 |  |  |  |  | 31745.98 |  | 0 |  | 0 |  | 0 | 0% |  | 31745.98
|  | M1-2. Duct Work | 74 | L/S | 1 |  |  |  |  | 121114.7918 |  | 0 |  | 0 |  | 0 | 0% |  | 121114.7918
|  | M1-3-1. Domestic Water | 74 | L/S | 1 |  |  |  |  | 31293.9869 |  | 0 |  | 6427.0832 |  | 6427.0832 | 20.54% |  | 24866.9038
|  | M1-3-2. Plumbing |  | L/S | 1 |  |  |  |  | 8248.5435 |  | 0 |  | 8248.5435 |  | 8248.5435 | 100% |  | 0
|  | M1-3-3 A/G NG Piping Work |  | L/S | 1 |  |  |  |  | 7303.9099 |  | 0 |  | 3175.875 |  | 3175.875 | 43.48% |  | 4128.035
|  | M1-4. Fire Protection Work |  | L/S | 1 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 | #DIV/0! |  | 0
|  | M1-5. Mechanical Demolition Work |  | L/S | 1 |  |  |  |  | 26262.949 |  | 0 |  | 0 |  | 0 | 0% |  | 26262.949
|  | M1-6. Civil WORK |  | L/S | 1 |  |  |  |  | 300981.67 |  | 0 |  | 0 |  | 0 | 0% |  | 300981.67
| 1.2 | 전기공사 |  | L/S | 1 |  |  |  |  | 473550.88 |  | 0 | 0 | 68365.84 | 0 | 68365.84 | 14.44% |  | 405185.04
|  | 01. POWER DISTRIBUTION WORK | 74 | L/S | 1 |  |  |  |  | 146204.14 |  | 0 |  | 68365.84 |  | 68365.84 | 46.76% |  | 77838.3
|  | 02. MECHANICAL POWER WORK | 74 | L/S | 1 |  |  |  |  | 140971.86 |  | 0 |  | 0 |  | 0 | 0% |  | 140971.86
|  | 03. Lighting WORK |  | L/S | 1 |  |  |  |  | 63568.46 |  | 0 |  | 0 |  | 0 | 0% |  | 63568.46
|  | 04. Receptacle WORK | 74 | L/S | 1 |  |  |  |  | 48825.62 |  | 0 |  | 0 |  | 0 | 0% |  | 48825.62
|  | 05. INCIDENTAL EXPENSE | 74 | L/S | 1 |  |  |  |  | 73980.8 |  | 0 |  | 0 |  | 0 | 0% |  | 73980.8
|  | 06. FIRE ALARM SYSTEM | 74 | L/S | 1 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 | #DIV/0! |  | 0
|  | Round Off | [7 empty] | -820.36 |  | 0 |  | -344.42 |  | -344.42
|  | TOTAL | [7 empty] | 1789000 |  | 0 |  | 218000 |  | 218000 |  |  | 1298289.8 | 10900 |  |  | 1
| 0 | 건축공사
| 1 | 1) TEMPORARY
| 2 | Demolition of Fence |  | LF | 200 | 0 | 14.11 |  | 14.11 | 2822 |  | 0 |  | 0 | 0 | 0 | 0% | 200 | 2822
| 3 | WIRE MESHED FENCE (Permanent Fence) | H:8', Incl. Footing Included, Color : RAL 9010, 6 Gauge | LF | 200 | 33.94 | 56.02 |  | 89.96 | 17992 |  | 0 |  | 0 | 0 | 0 | 0% | 200 | 17992
| 4 | Temporary Fence - Fixed Type | H=8', Galvanized Chain link fence, Including Entrance door | LF | 600 | 10.72 | 17.18 |  | 27.9 | 16740 |  | 0 |  | 0 | 0 | 0 | 0% | 600 | 16740 |  |  | 0
5
| 6 | [ Sub Total ] | [7 empty] | 37554 |  | 0 |  | 0 |  | 0 | 0% |  | 37554 |  |  | 0
| 7 | 2) DOOR, WINDOW | [19 empty] | 0
| 8 | SINGLE STEEL DOOR | Supply and install, hollow metal frame and door, including hardware set with glass, Size: 3' X 7' | EA | 5 | 1295.56 | 927.82 |  | 2223.38 | 11116.9 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 11116.9 |  |  | 0
| 9 | DOUBLE STEEL DOOR | Supply and install, hollow metal frame and door, including hardware set with glass, Size: 6' X 7' | EA | 1 | 2323.08 | 1391.8 |  | 3714.88 | 3714.88 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 3714.88 |  |  | 0
| 10 | SINGLE SWINGING DOOR | Supply and install frame and door, including hardware set with 16" x 16" and and 1/4" glass, Size: 3' X 7' | EA | 1 | 1518.93 | 973.77 |  | 2492.7 | 2492.7 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2492.7 |  |  | 0
| 11 | DOUBLE SWINGING DOOR | Supply and install frame and door, including hardware set with 16" x 16" and and 1/4" glass, Size: 6' X 7' | EA | 2 | 2680.48 | 1499 |  | 4179.48 | 8358.96 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 8358.96 |  |  | 0
| 12 | [20 empty] | 0
| 13 | [ Sub Total ] | [7 empty] | 25683.44 |  | 0 |  | 0 |  | 0 | 0% |  | 25683.44 |  |  | 0
| 14 | 3) DRYWALL | [19 empty] | 0
| 15 | Dry Wall(Water resistant) one side | 1 layer Water-resistant Gypsum board + 6" C-stud O.C 16" with bridge channel + insulation | LF2 | 2088 | 2.75 | 7.24 |  | 9.99 | 20859.12 |  | 0 | 1044 | 10429.56 | 1044 | 10429.56 | 50% | 1044 | 10429.56 |  |  | 0
| 16 | Dry Wall(Water resistant) both side | 1 layer Water-resistant Gypsum board + 6" C-stud O.C 16" with bridge channel + insulation + 1 layer Water-resistant Gypsum board | LF2 | 1885 | 3.92 | 9.55 |  | 13.47 | 25390.95 |  | 0 | 942.5 | 12695.475 | 942.5 | 12695.475 | 50% | 942.5 | 12695.475 |  |  | 0
| 17 | Dry Wall one side | 1 layer Gypsum board + 6" C-stud O.C 16" with bridge channel + insulation | LF2 | 553 | 2.5 | 6.93 |  | 9.43 | 5214.79 |  | 0 | 276.5 | 2607.395 | 276.5 | 2607.395 | 50% | 276.5 | 2607.395 |  |  | 0
| 18 | Dry Wall both side | 1 layer Gypsum board + 6" C-stud O.C 16" with bridge channel + insulation + 1 layer Gypsum board | LF2 | 2906 | 3.57 | 8.94 |  | 12.51 | 36354.06 |  | 0 | 1453 | 18177.03 | 1453 | 18177.03 | 50% | 1453 | 18177.03 |  |  | 0
| 19 | PENETRATION SEAL | Seal the wall penetrations within the ceiling using fire-rated sealant or general sealant to make air-tight and sound-tight | LF2 | 320 | 2.21 | 7.68 |  | 9.89 | 3164.8 |  | 0 |  | 0 | 0 | 0 | 0% | 320 | 3164.8 |  |  | 0
| 20 | REINFORCEMENT FOR DRY WALL | Reinforcement of structure for Dry wall around the opening caused by mechanical, eletrical, other works | LF2 | 320 | 2.67 | 8.47 |  | 11.14 | 3564.8 |  | 0 |  | 0 | 0 | 0 | 0% | 320 | 3564.8 |  |  | 0
| 21 | [20 empty] | 0
| 22 | [ Sub Total ] | [7 empty] | 94548.52 |  | 0 |  | 43909.46 |  | 43909.46 | 46.44% |  | 50639.06 |  |  | 0
| 23 | 4) WALL FINISH | [19 empty] | 0
| 24 | Water Paint | Primer(1 coat) + Top Coat(2 Coats), Joint and surface treatment included. Color : RAL 9010/9006 and Varied | LF2 | 6182 | 0.48 | 2.31 |  | 2.79 | 17247.78 |  | 0 |  | 0 | 0 | 0 | 0% | 6182 | 17247.78 |  |  | 0
| 25 | Stainless Steel Wall | THK : 3/8", Grade 316, Epoxy adhesive, edge/corner treatment(rounded),mirror finish,joint welding included | LF2 | 311 | 46.53 | 51.11 |  | 97.64 | 30366.04 |  | 0 |  | 0 | 0 | 0 | 0% | 311 | 30366.04 |  |  | 0
| 26 | Polyurethane Liquid Membrane Waterproofing(Kitchen) | Wall, Include Surface treatment and chamfer/patch up. Apply floors and walls Ponding test(min 24 hrs) required | LF2 | 1019 | 2.86 | 7.37 |  | 10.23 | 10424.37 |  | 0 |  | 0 | 0 | 0 | 0% | 1019 | 10424.37 |  |  | 0
| 27 | Stainless Steel Base | Supply an install 4" high Stainless steel plate base on walls | LF | 231.25 | 8.04 | 13.88 |  | 21.92 | 5069 |  | 0 |  | 0 | 0 | 0 | 0% | 231.25 | 5069 |  |  | 0
| 28 | FRP Panel | Fiber Reinforced Plastic Panel | LF2 | 1500 | 3.03 | 5.37 |  | 8.4 | 12600 |  | 0 |  | 0 | 0 | 0 | 0% | 1500 | 12600 |  |  | 0
| 29 | PVC Panel | Moisture resistance | LF2 | 1000 | 2.5 | 5.07 |  | 7.57 | 7570 |  | 0 |  | 0 | 0 | 0 | 0% | 1000 | 7570 |  |  | 0
| 30 | [20 empty] | 0
| 31 | [ Sub Total ] | [7 empty] | 83277.19 |  | 0 |  | 0 |  | 0 | 0% |  | 83277.19 |  |  | 0
| 32 | 5) FLOOR FINISH | [19 empty] | 0
| 33 | Concrete Demolition of less than 2CY at once | Perimeter wall,Reinforcement bar cutting and cutting surfrace treatement and rubbish disposal included | YD3 | 10 | 0 | 785.93 |  | 785.93 | 7859.3 |  | 0 |  | 0 | 0 | 0 | 0% | 10 | 7859.3 |  |  | 0
| 34 | Floor concrete | 2500 psi, premixed concrete, Supplying material, Pouring and vibrating, Leveling, including formwork and all submaterials. Machine trowel & manual steel trowel where machine cannot enter, w/ chamfered edge at pads & exposed structures, including all necessary works and submaterials. | YD3 | 2 | 196.54 | 733.26 |  | 929.8 | 1859.6 |  | 0 | 2 | 1859.6 | 2 | 1859.6 | 100% | 0 | 0 |  |  | 0
| 35 | Reinforcement Bars | #3, #4, #5, #6, #7, #8, #9. etc. | TON | 1 | 1295.56 | 2013.36 |  | 3308.92 | 3308.92 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 3308.92 |  |  | 0
| 36 | Ucrete Polyurethane Coating | Include cocnrete floor grinding and all requirements recommended by the manufacturer. Color will be applied. BASF UCRETE DP or equivalent | LF2 | 1800 | 6.69 | 9.72 |  | 16.41 | 29538 |  | 0 |  | 0 | 0 | 0 | 0% | 1800 | 29538 |  |  | 0
| 37 | Floor surface preparation and protection work |  | LF2 | 1800 | 1.06 | 4.63 |  | 5.69 | 10242 |  | 0 |  | 0 | 0 | 0 | 0% | 1800 | 10242 |  |  | 0
| 38 | Epoxy Coating | Primer + Epoxy Coating | LF2 | 1800 | 1.96 | 4.61 |  | 6.57 | 11826 |  | 0 |  | 0 | 0 | 0 | 0% | 1800 | 11826 |  |  | 0
| 39 | Vinyl Composite Tile | Supply and install Armstrong Premium Excelon Raffia Stream or equivalent. Include adhesive and misc. materials. Surface treatment included. Material grade shall be Luxury Vinyl Tile. 2 times floor waxing included. | LF2 | 200 | 3.57 | 11.38 |  | 14.95 | 2990 |  | 0 |  | 0 | 0 | 0 | 0% | 200 | 2990 |  |  | 0
| 40 | [20 empty] | 0
| 41 | [ Sub Total ] | [7 empty] | 67623.82 |  | 0 |  | 1859.6 |  | 1859.6 | 2.75% |  | 65764.22 |  |  | 0
| 42 | 6) CEILING FINISH | [19 empty] | 0
| 43 | Acoustic Ceiling Tile | Supply and install 2'X2' USG-HALCYON or equivalent. Ceiling panels for Narrow Grid, include thred bolt supported and t-bar grid system including required accessories and misc. materials | LF2 | 640 | 3.74 | 6.31 |  | 10.05 | 6432 |  | 0 |  | 0 | 0 | 0 | 0% | 640 | 6432 |  |  | 0
| 44 | SMC Ceiling Tile | Supply and install SMC ceiling including all steel structure support and clip-bar,channels and hangers and all accessories required for installation. | LF2 | 1800 | 8.48 | 13.11 |  | 21.59 | 38862 |  | 0 |  | 0 | 0 | 0 | 0% | 1800 | 38862 |  |  | 0
| 45 | [20 empty] | 0
| 46 | [ Sub Total ] | [7 empty] | 45294 |  | 0 |  | 0 |  | 0 | 0% |  | 45294 |  |  | 0
| 47 | 7) MISCELLANEOUS | [19 empty] | 0
| 48 | Bollard Demolition |  | EA | 7 | 0 | 244.11 |  | 244.11 | 1708.77 |  | 0 |  | 0 | 0 | 0 | 0% | 7 | 1708.77 |  |  | 0
| 49 | Grease Trap(Grease Interceptor) | Capacity : 1,500 GL, Include all electric cable&conduit wiring,clean-out drain,connection between the sample well and clean-out drain. Main DB panel and Service alert panel connection, all concrete structures and elements composing of Grease interceptor system. all civi works(excavation,GAB grading and compaction, Lean concrete), referring to Dwg 410-A-901 | SET | 2 | 22516.08 | 39297.34 |  | 61813.42 | 123626.84 |  | 0 | 0.6 | 37088.052 | 0.6 | 37088.052 | 30% | 1.4 | 86538.788 |  |  | 0
| 50 | Reinforcement (Roof Opening) | Refer to Section & Details for site modification work for reinforcement. Modification of Existing Steel Structure Member to enable New Strucutures such as Girth, Truss, Angle and Etc. to be able to be instllaed and connected without obstuction. - Cutting off any obsturcting structure and materials - Re-Instatement of cutted off materials and structure - Welding & Touch Up Paint also Included - All Accessories necessary required also Included - Erection by using of Crane & Boom lift included | TON | 1 | 2859.17 | 13025.59 |  | 15884.76 | 15884.76 |  | 0 | 1 | 15884.76 | 1 | 15884.76 | 100% | 0 | 0 |  |  | 0
| 51 | Remove Existing Roof Deck | Remove existing Roof Deck, incl. disposal to out of site | LF2 | 100 | 0.43 | 10.16 |  | 10.59 | 1059 |  | 0 |  | 0 | 0 | 0 | 0% | 100 | 1059 |  |  | 0
| 52 | TPO Patch | Membrane 60mil TPO | LF2 | 300 | 3.12 | 8.5 |  | 11.62 | 3486 |  | 0 |  | 0 | 0 | 0 | 0% | 300 | 3486 |  |  | 0
| 53 | Miscellaneous Steel works | Supply and installation of Structural Reinforcement steel for Canopy, Incl. Structural Calculations | TON | 1 | 3395.28 | 7366.35 |  | 10761.63 | 10761.63 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 10761.63 |  |  | 0
| 54 | CANOPY | Supply and install Vestibule Canopy(size 14'x5'x3', ACM) including the sub-structure, inlet, downspout, aluminum ceiling tile, roof membrane and other accessories for installation | EA | 1 | 8488.19 | 11710.61 |  | 20198.8 | 20198.8 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 20198.8 |  |  | 0
| 55 | Grating | For Trench, 1 3/4"x3/16" MTL BAR Grating(Galv.) | LF2 | 55 | 25.01 | 21.66 |  | 46.67 | 2566.85 |  | 0 |  | 0 | 0 | 0 | 0% | 55 | 2566.85 |  |  | 0
| 56 | Trench-1 | W36" X H6", embedded steel profiles(incl. angle), all sub-material. | LF | 11 | 196.54 | 496.8 |  | 693.34 | 7626.74 |  | 0 |  | 0 | 0 | 0 | 0% | 11 | 7626.74 |  |  | 0
| 57 | Trench-2 | W16" X H6", embedded steel profiles(incl. angle), all sub-material. | LF | 5 | 134.02 | 388.45 |  | 522.47 | 2612.35 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 2612.35 |  |  | 0
| 58 | Trench-3 | W19" X H6", embedded steel profiles(incl. angle), all sub-material. | LF | 7 | 147.42 | 403.78 |  | 551.2 | 3858.4 |  | 0 |  | 0 | 0 | 0 | 0% | 7 | 3858.4 |  |  | 0
| 59 | [20 empty] | 0
| 60 | [ Sub Total ] | [7 empty] | 193390.14 |  | 0 |  | 52972.812 |  | 52972.812 | 27.39% |  | 16664.34 |  |  | 0
| 61 | 8) TOLIET WORKS | [19 empty] | 0
| 62 | Water Proofing | Supply and install Elastic Liquid-applied memberane water proof(Floor+Vertical), or equivalent, including the required adhesive, corner bead and misc. materials for installation. | LF2 | 597 | 4 | 9.31 |  | 13.31 | 7946.07 |  | 0 |  | 0 | 0 | 0 | 0% | 597 | 7946.07 |  |  | 0
| 63 | Urinal Partition | Supply and install Laminated toilet parition(Laminate shall be water-resistance). Include all hardware set and accessories. Design proposed by the Subontractor and approved by the Contractor(no additional claim) | EA | 3 | 848.81 | 618.2 |  | 1467.01 | 4401.03 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 4401.03 |  |  | 0
| 64 | Mirror | Thickness : 1/4", include frame(if the Contractor requests) | LF2 | 38 | 19.65 | 21.66 |  | 41.31 | 1569.78 |  | 0 |  | 0 | 0 | 0 | 0% | 38 | 1569.78 |  |  | 0
| 65 | ADA GRAB BAR | Refer to Fixture document | EA | 4 | 84.88 | 112.68 |  | 197.56 | 790.24 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 790.24 |  |  | 0
| 66 | Mop Sink | Refer to Fixture document | EA | 1 | 696.92 | 725.41 |  | 1422.33 | 1422.33 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1422.33 |  |  | 0
| 67 | Mop Sink Faucet | Refer to Fixture document | EA | 1 | 285.91 | 308.52 |  | 594.43 | 594.43 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 594.43 |  |  | 0
| 68 | Vanity Counter | 12'-1" PIPE STRUCTURE REINFORCEMENT + CONTER TOP | LF | 10 | 187.62 | 231.95 |  | 419.57 | 4195.7 |  | 0 |  | 0 | 0 | 0 | 0% | 10 | 4195.7 |  |  | 0
| 69 | Vanity Bowl Faucet | Refer to Fixture document | EA | 2 | 339.51 | 323.83 |  | 663.34 | 1326.68 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 1326.68 |  |  | 0
| 70 | Urinal | Refer to Fixture document | EA | 2 | 643.31 | 647.68 |  | 1290.99 | 2581.98 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 2581.98 |  |  | 0
| 71 | URINAL FLUSH VALVE | Refer to Fixture document | EA | 2 | 375.26 | 308.52 |  | 683.78 | 1367.56 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 1367.56 |  |  | 0
| 72 | Paper Towel Dispenser | Refer to Fixture document | EA | 2 | 142.95 | 123.63 |  | 266.58 | 533.16 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 533.16 |  |  | 0
| 73 | Toilet Paper Dispenser | Refer to Fixture document | EA | 2 | 84.88 | 97.39 |  | 182.27 | 364.54 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 364.54 |  |  | 0
| 74 | Seat Cover Dispenser | Refer to Fixture document | EA | 2 | 75.94 | 97.39 |  | 173.33 | 346.66 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 346.66 |  |  | 0
| 75 | Ada Toilet Closet Bowl | Refer to Fixture document | EA | 2 | 759.46 | 717.18 |  | 1476.64 | 2953.28 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 2953.28 |  |  | 0
| 76 | TOILET CLOSET BOWL ADA FLUSH VALVE | Refer to Fixture document | EA | 2 | 402.06 | 323.83 |  | 725.89 | 1451.78 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 1451.78 |  |  | 0
| 77 | [20 empty] | 0
| 78 | [ Sub Total ] | [7 empty] | 31845.22 |  | 0 |  | 0 |  | 0 | 0% |  | 4751.72 |  |  | 0
| 79 | 9) CIVIL WORKS | [19 empty] | 0
| 80 | Sanitary Sewer Line - Size Change | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 81 | Demolition Work | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 82 | Demolition of Fence |  | LF | 30 | 0 | 14.11 |  | 14.11 | 423.3 |  | 0 |  | 0 | 0 | 0 | 0% | 30 | 423.3 |  |  | 0
| 83 | Demolition of Concrete (Curb&Gutter) | Length of Curb&Gutter = 30.00 LF / with GAB under the C&G | YD3 | 1 | 0 | 1042.19 |  | 1042.19 | 1042.19 |  | 0 | 0.3 | 312.657 | 0.3 | 312.657 | 30% | 0.7 | 729.533 |  |  | 0
| 84 | Demolition of Asphalt (Asphalt Cutting Length) | with Asphalt Cutting | LF | 130 | 0 | 33.18 |  | 33.18 | 4313.4 |  | 0 | 39 | 1294.02 | 39 | 1294.02 | 30% | 91 | 3019.38 |  |  | 0
| 85 | Demolition of GAB | with Cutting Soil | YD3 | 22 | 0 | 134.64 |  | 134.64 | 2962.08 |  | 0 | 6.6 | 888.624 | 6.6 | 888.624 | 30% | 15.4 | 2073.456 |  |  | 0
| 86 | Restoration Work (Pavement) | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 87 | Installation of Concrete Curb&Gutter |  | LF | 30 | 16.07 | 59.3 |  | 75.37 | 2261.1 |  | 0 |  | 0 | 0 | 0 | 0% | 30 | 2261.1 |  |  | 0
| 88 | GAB down and compaction | For Curb&Gutter | YD3 | 1 | 49.14 | 173.49 |  | 222.63 | 222.63 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 222.63 |  |  | 0
| 89 | Asphalt Paving (Binder) | T=3.5" | FT2 | 895 | 2.12 | 4.7 |  | 6.82 | 6103.9 |  | 0 |  | 0 | 0 | 0 | 0% | 895 | 6103.9 |  |  | 0
| 90 | Tack Coating | RSC-4 (30 ℓ/a) | FT2 | 895 | 0.12 | 0.61 |  | 0.73 | 653.35 |  | 0 |  | 0 | 0 | 0 | 0% | 895 | 653.35 |  |  | 0
| 91 | Asphalt Paving (Surface) | T=2.0" | FT2 | 895 | 1.42 | 3.78 |  | 5.2 | 4654 |  | 0 |  | 0 | 0 | 0 | 0% | 895 | 4654 |  |  | 0
| 92 | GAB down and compaction | For Asphalt Pavement | YD3 | 22 | 49.14 | 173.49 |  | 222.63 | 4897.86 |  | 0 |  | 0 | 0 | 0 | 0% | 22 | 4897.86 |  |  | 0
| 93 | Installation of Wire Meshed Fence |  | LF | 30 | 33.94 | 56.02 |  | 89.96 | 2698.8 |  | 0 |  | 0 | 0 | 0 | 0% | 30 | 2698.8 |  |  | 0
| 94 | Line Striping for road | W5", Solid White & W5", Dashed / White&Yellow | LF | 90 | 1.06 | 6.75 |  | 7.81 | 702.9 |  | 0 |  | 0 | 0 | 0 | 0% | 90 | 702.9 |  |  | 0
| 95 | Restoration Work of Damaged other Pipe | Cost for repair in the event of damage to other utilities during construction (quantity shall be zero if no damage occurs). | L/S | 1 | 0 | 8218.62 |  | 8218.62 | 8218.62 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 8218.62 |  |  | 0
| 96 | Secondary Containment System | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 97 | Demolition Work | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 98 | Demolition of Concrete (Top of Pit, 3ft) |  | YD3 | 16 | 0 | 1042.19 |  | 1042.19 | 16675.04 |  | 0 |  | 0 | 0 | 0 | 0% | 16 | 16675.04 |  |  | 0
| 99 | Pit Backfilling Work | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 100 | Placement of hauling dirt / fine grading (Inc. Pit) | Compacted lifts : T=8" at maximum Compaction Density : 98% | YD3 | 343 | 10.72 | 47.71 |  | 58.43 | 20041.49 |  | 0 | 343 | 20041.49 | 343 | 20041.49 | 100% | 0 | 0 |  |  | 0
| 101 | Fine grading & Compaction before lay down Gravel | Compacted lifts : T=8" at maximum Compaction Density : 98% | FT2 | 1296 | 0.3 | 1.97 |  | 2.27 | 2941.92 |  | 0 | 1296 | 2941.92 | 1296 | 2941.92 | 100% | 0 | 0 |  |  | 0
| 102 | Underground Pipe | HDPE 12", Inc. Sub Material | LF | 45 | 33.94 | 141.76 |  | 175.7 | 7906.5 |  | 0 | 45 | 7906.5 | 45 | 7906.5 | 100% | 0 | 0 |  |  | 0
| 103 | Asphalt Paving Work - Additional Parking Lot | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 104 | Demolition of Concrete (Curb&Gutter) | Length of Curb&Gutter = 36.95 LF | YD3 | 1 | 0 | 1042.19 |  | 1042.19 | 1042.19 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1042.19 |  |  | 0
| 105 | Installation of Concrete Curb&Gutter |  | LF | 391 | 16.07 | 59.3 |  | 75.37 | 29469.67 |  | 0 |  | 0 | 0 | 0 | 0% | 391 | 29469.67 |  |  | 0
| 106 | GAB down and compaction | For Curb&Gutter / Asphalt Paving | YD3 | 14 | 49.14 | 173.49 |  | 222.63 | 3116.82 |  | 0 |  | 0 | 0 | 0 | 0% | 14 | 3116.82 |  |  | 0
| 107 | Reinstallation of Asphalt Paving (Binder) | T=2.5" | FT2 | 332 | 1.96 | 4.41 |  | 6.37 | 2114.84 |  | 0 |  | 0 | 0 | 0 | 0% | 332 | 2114.84 |  |  | 0
| 108 | Tack Coating | RSC-4 (30 ℓ/a) | FT2 | 332 | 0.12 | 0.61 |  | 0.73 | 242.36 |  | 0 |  | 0 | 0 | 0 | 0% | 332 | 242.36 |  |  | 0
| 109 | Reinstallation of Asphalt Paving (Surface) | T=2.0" | FT2 | 332 | 1.42 | 3.78 |  | 5.2 | 1726.4 |  | 0 |  | 0 | 0 | 0 | 0% | 332 | 1726.4 |  |  | 0
| 110 | Restoration Work | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 111 | Restoration other Pavement | Cost for repair in the event of damage to other Pavement during construction (quantity shall be zero if no damage occurs). | L/S | 1 | 0 | 4931.17 |  | 4931.17 | 4931.17 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 4931.17 |  |  | 0
| 112 | Water Line - Capacity | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 113 | Crossing Work (Assist the Electrical Work) | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 114 | Demolition of Concrete (Curb&Gutter) | Length of Curb&Gutter = 30.00 LF | YD3 | 1 | 0 | 1042.19 |  | 1042.19 | 1042.19 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1042.19 |  |  | 0
| 115 | Demolition of Asphalt (Asphalt Cutting Length) | with Asphalt Cutting / Inc. Waste disposal | LF | 116 | 0 | 33.18 |  | 33.18 | 3848.88 |  | 0 |  | 0 | 0 | 0 | 0% | 116 | 3848.88 |  |  | 0
| 116 | Demolition of Concrete (Dock) | Area of Dock = 230.73 SF | YD3 | 6 | 0 | 1169.22 |  | 1169.22 | 7015.32 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 7015.32 |  |  | 0
| 117 | Demolition of GAB | Curb&Gutter / Dock | YD3 | 12 | 0 | 134.64 |  | 134.64 | 1615.68 |  | 0 |  | 0 | 0 | 0 | 0% | 12 | 1615.68 |  |  | 0
| 118 | Installation of Concrete Curb&Gutter |  | LF | 27 | 16.07 | 59.3 |  | 75.37 | 2034.99 |  | 0 |  | 0 | 0 | 0 | 0% | 27 | 2034.99 |  |  | 0
| 119 | GAB down and compaction | For Curb&Gutter / Dock / Asphalt Paving | YD3 | 12 | 49.14 | 173.49 |  | 222.63 | 2671.56 |  | 0 |  | 0 | 0 | 0 | 0% | 12 | 2671.56 |  |  | 0
| 120 | Concrete paving(Dock) | T=8.0" | YD3D | 6 | 214.43 | 812.07 |  | 1026.5 | 6159 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 6159 |  |  | 0
| 121 | Reinstallation of Asphalt Paving (Binder) | T=2.5" | FT2 | 310 | 1.96 | 4.41 |  | 6.37 | 1974.7 |  | 0 |  | 0 | 0 | 0 | 0% | 310 | 1974.7 |  |  | 0
| 122 | Tack Coating | RSC-4 (30 ℓ/a) | FT2 | 310 | 0.12 | 0.61 |  | 0.73 | 226.3 |  | 0 |  | 0 | 0 | 0 | 0% | 310 | 226.3 |  |  | 0
| 123 | Reinstallation of Asphalt Paving (Surface) | T=2.0" | FT2 | 310 | 1.42 | 3.78 |  | 5.2 | 1612 |  | 0 |  | 0 | 0 | 0 | 0% | 310 | 1612 |  |  | 0
| 124 | Restoration Work of Damaged other Pipe | Cost for repair in the event of damage to other utilities during construction (quantity shall be zero if no damage occurs). | L/S | 1 | 0 | 8218.62 |  | 8218.62 | 8218.62 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 8218.62 |  |  | 0
| 125 | [20 empty] | 0
| 126 | [ Sub Total ] | [7 empty] | 165781.77 |  | 0 |  | 33385.211 |  | 33385.211 | 20.14% |  | 10056.92 |  |  | 0
| 127 | [ 건축공사 Total ] | [7 empty] | 744998.1 |  | 0 |  | 132127.083 |  | 132127.083 | 17.74% |  | 339684.89 |  |  | 0
| 128 | 설비공사 | [19 empty] | 0
| 129 | M0 General | [19 empty] | 0
| 130 | M1-0 General | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0
| 131 | Design & Engineering Review | Shop DWG As built Inspection Authorization Testing, Adjusting and Balancing etc, as per specification | SET | 1 | 0 | 44319.55 |  | 44319.55 | 44319.55 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 44319.55 |  |  | 0
| 132 | [20 empty] | 0
| 133 | [ Sub Total ] | [7 empty] | 44319.55 |  | 0 |  | 0 |  | 0 | 0% |  | 44319.55 |  |  | 0
| 134 | M1-1. Equipment | [19 empty] | 0
| 135 | SF-703-01 | 2700 CFM | SET | 1 | 0 | 2645.5 |  | 2645.5 | 2645.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2645.5 |  |  | 0
| 136 | SF-703-02 | 2700 CFM | SET | 1 | 0 | 2645.5 |  | 2645.5 | 2645.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2645.5 |  |  | 0
| 137 | EF-703-01 | 100 CFM | SET | 1 | 0 | 1322.75 |  | 1322.75 | 1322.75 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1322.75 |  |  | 0
| 138 | EF-703-02 | 300 CFM | SET | 1 | 0 | 1322.75 |  | 1322.75 | 1322.75 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1322.75 |  |  | 0
| 139 | EF-703-03 | 200 CFM | SET | 1 | 0 | 1322.75 |  | 1322.75 | 1322.75 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1322.75 |  |  | 0
| 140 | EF-703-04 | 500 CFM | SET | 1 | 0 | 1322.75 |  | 1322.75 | 1322.75 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1322.75 |  |  | 0
| 141 | EF-703-05 | 1200 CFM | SET | 1 | 0 | 2645.5 |  | 2645.5 | 2645.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2645.5 |  |  | 0
| 142 | EF-703-06 | 2600 CFM | SET | 1 | 0 | 2645.5 |  | 2645.5 | 2645.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2645.5 |  |  | 0
| 143 | EF-703-07 | 2600 CFM | SET | 1 | 0 | 2645.5 |  | 2645.5 | 2645.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2645.5 |  |  | 0
| 144 | EF-703-08 | 3100 CFM | SET | 1 | 0 | 2645.5 |  | 2645.5 | 2645.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2645.5 |  |  | 0
| 145 | EF-703-09 | 100 CFM | SET | 1 | 0 | 1322.75 |  | 1322.75 | 1322.75 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1322.75 |  |  | 0
| 146 | EF-703-10 | 100 CFM | SET | 1 | 0 | 1322.75 |  | 1322.75 | 1322.75 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1322.75 |  |  | 0
| 147 | AC-709-01 (w/Dryer, Filters, etc) | 1130 CFM | SET | 1 | 0 | 3174.6 |  | 3174.6 | 3174.6 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 3174.6 |  |  | 0
| 148 | AC-709-02 (w/Dryer, Filters, etc) | 388 CFM | SET | 1 | 0 | 3174.6 |  | 3174.6 | 3174.6 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 3174.6 |  |  | 0
| 149 | CU-709-01 | 3HP | SET | 1 | 0 | 793.64 |  | 793.64 | 793.64 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 793.64 |  |  | 0
| 150 | CU-709-02 | 1HP | SET | 1 | 0 | 793.64 |  | 793.64 | 793.64 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 793.64 |  |  | 0
| 151 | [20 empty] | 0
| 152 | [ Sub Total ] | [7 empty] | 31745.98 |  | 0 |  | 0 |  | 0 | 0% |  | 31745.98 |  |  | 0
| 153 | M1-2. Duct Work | [19 empty] | 0
| 154 | Galvanized Steel Duct Installation - Galvanised duct based on SMACNA Standard_#26 (0.55T) | Include wall and ceiling penetration filling, fire-resistant material for the firewall finish, flexible duct, canvas joint, insect screen, reinforcement, accessories, supports, sleeves, openning, inserts, etc. | M2 | 45.88 | 0 | 154.76 |  | 154.76 | 7100.3888 |  | 0 |  | 0 | 0 | 0 | 0% | 45.88 | 7100.3888 |  |  | 0
| 155 | Galvanized Steel Duct Installation - Galvanised duct based on SMACNA Standard_#24 (0.6T) | Include wall and ceiling penetration filling, fire-resistant material for the firewall finish, flexible duct, canvas joint, insect screen, reinforcement, accessories, supports, sleeves, openning, inserts, etc. | M2 | 86.18 | 0 | 139.23 |  | 139.23 | 11998.8414 |  | 0 |  | 0 | 0 | 0 | 0% | 86.18 | 11998.8414 |  |  | 0
| 156 | Galvanized Steel Duct Installation - Galvanised duct based on SMACNA Standard_#22 (0.85T) | Include wall and ceiling penetration filling, fire-resistant material for the firewall finish, flexible duct, canvas joint, insect screen, reinforcement, accessories, supports, sleeves, openning, inserts, etc. | M2 | 3.71 | 0 | 154.76 |  | 154.76 | 574.1596 |  | 0 |  | 0 | 0 | 0 | 0% | 3.71 | 574.1596 |  |  | 0
| 157 | STAINLESS Steel Duct Installation(Welding) - #18 (1.2T) | Include wall and ceiling penetration filling, fire-resistant material for the firewall finish, flexible duct, canvas joint, insect screen, reinforcement, accessories, supports, sleeves, openning, inserts, etc. | M2 | 19.79 | 0 | 309.1 |  | 309.1 | 6117.089 |  | 0 |  | 0 | 0 | 0 | 0% | 19.79 | 6117.089 |  |  | 0
| 158 | STAINLESS Steel Duct Installation(Welding) - #16 (1.6T) | Include wall and ceiling penetration filling, fire-resistant material for the firewall finish, flexible duct, canvas joint, insect screen, reinforcement, accessories, supports, sleeves, openning, inserts, etc. | M2 | 50.36 | 0 | 464.13 |  | 464.13 | 23373.5868 |  | 0 |  | 0 | 0 | 0 | 0% | 50.36 | 23373.5868 |  |  | 0
| 159 | Round Duct | 200A | M | 15.99 | 0 | 126.62 |  | 126.62 | 2024.6538 |  | 0 |  | 0 | 0 | 0 | 0% | 15.99 | 2024.6538 |  |  | 0
| 160 | Round Duct | 300A | M | 3.54 | 0 | 185.66 |  | 185.66 | 657.2364 |  | 0 |  | 0 | 0 | 0 | 0% | 3.54 | 657.2364 |  |  | 0
| 161 | Round Duct | 450A | M | 36.34 | 0 | 309.37 |  | 309.37 | 11242.5058 |  | 0 |  | 0 | 0 | 0 | 0% | 36.34 | 11242.5058 |  |  | 0
| 162 | Duct Insulation | As per specification | M2 | 261.79 | 0 | 128.38 |  | 128.38 | 33608.6002 |  | 0 |  | 0 | 0 | 0 | 0% | 261.79 | 33608.6002 |  |  | 0
| 163 | SQUARE DIFFUSER | ND150 | EA | 4 | 0 | 299.35 |  | 299.35 | 1197.4 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 1197.4 |  |  | 0
| 164 | SQUARE DIFFUSER | ND200 | EA | 1 | 0 | 299.35 |  | 299.35 | 299.35 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 299.35 |  |  | 0
| 165 | SQUARE DIFFUSER | ND250 | EA | 5 | 0 | 320.24 |  | 320.24 | 1601.2 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 1601.2 |  |  | 0
| 166 | SQUARE DIFFUSER | ND300 | EA | 3 | 0 | 320.24 |  | 320.24 | 960.72 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 960.72 |  |  | 0
| 167 | REGISTER | 200*150 | EA | 4 | 0 | 365.49 |  | 365.49 | 1461.96 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 1461.96 |  |  | 0
| 168 | REGISTER | 250*200 | EA | 1 | 0 | 365.49 |  | 365.49 | 365.49 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 365.49 |  |  | 0
| 169 | REGISTER | 250*250 | EA | 6 | 0 | 365.49 |  | 365.49 | 2192.94 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 2192.94 |  |  | 0
| 170 | REGISTER | 300*150 | EA | 1 | 0 | 365.49 |  | 365.49 | 365.49 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 365.49 |  |  | 0
| 171 | REGISTER | 300*300 | EA | 2 | 0 | 365.49 |  | 365.49 | 730.98 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 730.98 |  |  | 0
| 172 | REGISTER | 450*250 | EA | 3 | 0 | 365.49 |  | 365.49 | 1096.47 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 1096.47 |  |  | 0
| 173 | V.D | 200*150 | EA | 4 | 0 | 261.06 |  | 261.06 | 1044.24 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 1044.24 |  |  | 0
| 174 | V.D | 250*200 | EA | 1 | 0 | 261.06 |  | 261.06 | 261.06 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 261.06 |  |  | 0
| 175 | V.D | 250*250 | EA | 6 | 0 | 261.06 |  | 261.06 | 1566.36 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 1566.36 |  |  | 0
| 176 | V.D | 300*150 | EA | 1 | 0 | 261.06 |  | 261.06 | 261.06 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 261.06 |  |  | 0
| 177 | V.D | 300*300 | EA | 2 | 0 | 261.06 |  | 261.06 | 522.12 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 522.12 |  |  | 0
| 178 | V.D | 450*250 | EA | 3 | 0 | 339.39 |  | 339.39 | 1018.17 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 1018.17 |  |  | 0
| 179 | B.D.D | 8"x8" | EA | 3 | 0 | 261.06 |  | 261.06 | 783.18 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 783.18 |  |  | 0
| 180 | B.D.D | 12"x12" | EA | 6 | 0 | 261.06 |  | 261.06 | 1566.36 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 1566.36 |  |  | 0
| 181 | B.D.D | 18"x18" | EA | 6 | 0 | 339.39 |  | 339.39 | 2036.34 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 2036.34 |  |  | 0
| 182 | R.D | 8"x8" | EA | 3 | 0 | 217.89 |  | 217.89 | 653.67 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 653.67 |  |  | 0
| 183 | R.D | 12"x12" | EA | 6 | 0 | 253.4 |  | 253.4 | 1520.4 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 1520.4 |  |  | 0
| 184 | R.D | 18"x18" | EA | 6 | 0 | 253.4 |  | 253.4 | 1520.4 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 1520.4 |  |  | 0
| 185 | Identification | Apply to ducts and all dampers | LOT | 1 | 0 | 1392.37 |  | 1392.37 | 1392.37 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1392.37 |  |  | 0
| 186 | [20 empty] | 0
| 187 | [ Sub Total ] | [7 empty] | 121114.7918 |  | 0 |  | 0 |  | 0 | 0% |  | 121114.7918 |  |  | 0
| 188 | M1-3-1. Domestic Water | [19 empty] | 0
| 189 | STAINLESS STEEL PIPE ASTM A312-TP304, ERW | ¾", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, Anti-Corrosion Paint, According to the specified pipe joining methods. | M | 110.82 | 0 | 46.51 |  | 46.51 | 5154.2382 |  | 0 | 55.41 | 2577.1191 | 55.41 | 2577.1191 | 50% | 55.41 | 2577.1191 |  |  | 0
| 190 | STAINLESS STEEL PIPE ASTM A312-TP304, ERW | 1", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 28.6 | 0 | 55.79 |  | 55.79 | 1595.594 |  | 0 | 14.3 | 797.797 | 14.3 | 797.797 | 50% | 14.3 | 797.797 |  |  | 0
| 191 | STAINLESS STEEL PIPE ASTM A312-TP304, ERW | 1½", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 55.23 | 0 | 79.72 |  | 79.72 | 4402.9356 |  | 0 | 27.615 | 2201.4678 | 27.615 | 2201.4678 | 50% | 27.615 | 2201.4678 |  |  | 0
| 192 | STAINLESS STEEL PIPE ASTM A312-TP304, ERW | 2", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 10.97 | 0 | 87.25 |  | 87.25 | 957.1325 |  | 0 | 5.485 | 478.5663 | 5.485 | 478.5663 | 50% | 5.485 | 478.5663 |  |  | 0
| 193 | CPVC (ASTM D 2846) | ½", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 2.1 | 0 | 62 |  | 62 | 130.2 |  | 0 | 1.05 | 65.1 | 1.05 | 65.1 | 50% | 1.05 | 65.1 |  |  | 0
| 194 | CPVC (ASTM D 2846) | 1", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 3.4 | 0 | 69.74 |  | 69.74 | 237.116 |  | 0 | 1.7 | 118.558 | 1.7 | 118.558 | 50% | 1.7 | 118.558 |  |  | 0
| 195 | CPVC (ASTM D 2846) | 1½", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 5 | 0 | 75.39 |  | 75.39 | 376.95 |  | 0 | 2.5 | 188.475 | 2.5 | 188.475 | 50% | 2.5 | 188.475 |  |  | 0
| 196 | Pipe Insulation (Flexible Elastomeric Insulation) | D 20x25T, Included Pipe Shoe Insulation | M | 110.82 | 0 | 30.75 |  | 30.75 | 3407.715 |  | 0 |  | 0 | 0 | 0 | 0% | 110.82 | 3407.715 |  |  | 0
| 197 | Pipe Insulation (Flexible Elastomeric Insulation) | D 25x25T, Included Pipe Shoe Insulation | M | 34.1 | 0 | 33.75 |  | 33.75 | 1150.875 |  | 0 |  | 0 | 0 | 0 | 0% | 34.1 | 1150.875 |  |  | 0
| 198 | Pipe Insulation (Flexible Elastomeric Insulation) | D 40x25T, Included Pipe Shoe Insulation | M | 60.23 | 0 | 46.44 |  | 46.44 | 2797.0812 |  | 0 |  | 0 | 0 | 0 | 0% | 60.23 | 2797.0812 |  |  | 0
| 199 | Pipe Insulation (Flexible Elastomeric Insulation) | D 50x25T, Included Pipe Shoe Insulation | M | 10.97 | 0 | 55.02 |  | 55.02 | 603.5694 |  | 0 |  | 0 | 0 | 0 | 0% | 10.97 | 603.5694 |  |  | 0
| 200 | Ball valve | ¾" | EA | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 201 | Ball valve | 1" | EA | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 202 | Ball valve | 1½" | EA | 5 | 0 | 51.6 |  | 51.6 | 258 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 258 |  |  | 0
| 203 | Ball valve | 2" | EA | 1 | 0 | 51.6 |  | 51.6 | 51.6 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 51.6 |  |  | 0
| 204 | Valve Insulation | As per specification | Point | 16 | 0 | 225.99 |  | 225.99 | 3615.84 |  | 0 |  | 0 | 0 | 0 | 0% | 16 | 3615.84 |  |  | 0
| 205 | Strainer | ¾" | EA | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 206 | Strainer | 1" | EA | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 207 | Check Valve | ¾" | EA | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 208 | Check Valve | 1" | EA | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 209 | Relief Valve | ¾" | EA | 1 | 0 | 34.87 |  | 34.87 | 34.87 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 34.87 |  |  | 0
| 210 | Thermostatic Mixing Valve | TMV-1 | SET | 1 | 0 | 34.87 |  | 34.87 | 34.87 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 34.87 |  |  | 0
| 211 | Water Heater | WH-1 | SET | 1 | 0 | 34.87 |  | 34.87 | 34.87 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 34.87 |  |  | 0
| 212 | Expansion Tank | EX-1 | SET | 1 | 0 | 1046.28 |  | 1046.28 | 1046.28 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1046.28 |  |  | 0
| 213 | Recirculation Pump | RP-1 | SET | 1 | 0 | 1046.28 |  | 1046.28 | 1046.28 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1046.28 |  |  | 0
| 214 | URINAL Bracket | SINGLE | EA | 1 | 0 | 601.25 |  | 601.25 | 601.25 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 601.25 |  |  | 0
| 215 | Water Closet Bracket | SINGLE | EA | 2 | 0 | 601.25 |  | 601.25 | 1202.5 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 1202.5 |  |  | 0
| 216 | Water Closet Bracket | DOUBLE | EA | 1 | 0 | 601.25 |  | 601.25 | 601.25 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 601.25 |  |  | 0
| 217 | P.G (Carbon) | 0-35 KG/CM2 | SET | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 218 | T.G (Carbon) | L Type | SET | 2 | 0 | 34.87 |  | 34.87 | 69.74 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 69.74 |  |  | 0
| 219 | Identification | Apply to All Pipe & Valve | LOT | 1 | 0 | 1395.05 |  | 1395.05 | 1395.05 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1395.05 |  |  | 0
| 220 | [20 empty] | 0
| 221 | [ Sub Total ] | [7 empty] | 31293.9869 |  | 0 |  | 6427.0832 |  | 6427.0832 | 20.54% |  | 24866.9038 |  |  | 0
| 222 | M1-3-2. Plumbing | [19 empty] | 0
| 223 | PVC (ASTM D 1785) | 2", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 3 | 0 | 90.04 |  | 90.04 | 270.12 |  | 0 | 3 | 270.12 | 3 | 270.12 | 100% | 0 | 0 |  |  | 0
| 224 | PVC (ASTM D 1785) | 3", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 8.75 | 0 | 121.29 |  | 121.29 | 1061.2875 |  | 0 | 8.75 | 1061.2875 | 8.75 | 1061.2875 | 100% | 0 | 0 |  |  | 0
| 225 | PVC (ASTM D 1785) | 4", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, According to the specified pipe joining methods. | M | 23.52 | 0 | 155.05 |  | 155.05 | 3646.776 |  | 0 | 23.52 | 3646.776 | 23.52 | 3646.776 | 100% | 0 | 0 |  |  | 0
| 226 | Floor Drain | 3" | EA | 4 | 0 | 140.89 |  | 140.89 | 563.56 |  | 0 | 4 | 563.56 | 4 | 563.56 | 100% | 0 | 0 |  |  | 0
| 227 | Floor Drain | 4" | EA | 4 | 0 | 152.75 |  | 152.75 | 611 |  | 0 | 4 | 611 | 4 | 611 | 100% | 0 | 0 |  |  | 0
| 228 | Floor Cleanout | 3" | EA | 4 | 0 | 140.89 |  | 140.89 | 563.56 |  | 0 | 4 | 563.56 | 4 | 563.56 | 100% | 0 | 0 |  |  | 0
| 229 | Floor Cleanout | 4" | EA | 4 | 0 | 152.75 |  | 152.75 | 611 |  | 0 | 4 | 611 | 4 | 611 | 100% | 0 | 0 |  |  | 0
| 230 | Wall Cleanout | 3" | EA | 1 | 0 | 140.89 |  | 140.89 | 140.89 |  | 0 | 1 | 140.89 | 1 | 140.89 | 100% | 0 | 0 |  |  | 0
| 231 | Wall Cleanout | 4" | EA | 1 | 0 | 152.75 |  | 152.75 | 152.75 |  | 0 | 1 | 152.75 | 1 | 152.75 | 100% | 0 | 0 |  |  | 0
| 232 | EXCAVAITION,BACK FILL AND SOIL DISPOAL | Excavaition for underground piping and soil disposal at site | M | 15 | 0 | 41.84 |  | 41.84 | 627.6 |  | 0 | 15 | 627.6 | 15 | 627.6 | 100% | 0 | 0 |  |  | 0
| 233 | [20 empty] | 0
| 234 | [ Sub Total ] | [7 empty] | 8248.5435 |  | 0 |  | 8248.5435 |  | 8248.5435 | 100% |  | 0 |  |  | 0
| 235 | M1-3-3 A/G NG Piping Work | [19 empty] | 0
| 236 | BLACK CARBON STEEL PIPE ASTM A53 GR B, ERW | ¾", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, Anti-Corrosion Paint, According to the specified pipe joining methods. | M | 3.08 | 0 | 70.57 |  | 70.57 | 217.3556 |  | 0 | 1.54 | 108.6778 | 1.54 | 108.6778 | 50% | 1.54 | 108.6778 |  |  | 0
| 237 | BLACK CARBON STEEL PIPE ASTM A53 GR B, ERW | 1", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, Anti-Corrosion Paint, According to the specified pipe joining methods. | M | 10.97 | 0 | 88.29 |  | 88.29 | 968.5413 |  | 0 | 5.485 | 484.2707 | 5.485 | 484.2707 | 50% | 5.485 | 484.2707 |  |  | 0
| 238 | BLACK CARBON STEEL PIPE ASTM A53 GR B, ERW | 1½", Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), sleeves, opennings, inserts, finishings around openings or sleeves, Supports, Anti-Corrosion Paint, According to the specified pipe joining methods. | M | 43.89 | 0 | 117.7 |  | 117.7 | 5165.853 |  | 0 | 21.945 | 2582.9265 | 21.945 | 2582.9265 | 50% | 21.945 | 2582.9265 |  |  | 0
| 239 | Ball valve (Gas) | ¾" | EA | 2 | 0 | 66.19 |  | 66.19 | 132.38 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 132.38 |  |  | 0
| 240 | Ball valve (Gas) | 1" | EA | 1 | 0 | 66.19 |  | 66.19 | 66.19 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 66.19 |  |  | 0
| 241 | Ball valve (Gas) | 1½" | EA | 3 | 0 | 97.97 |  | 97.97 | 293.91 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 293.91 |  |  | 0
| 242 | P.G (Carbon) (Gas) | 0-35 KG/CM2 | SET | 2 | 0 | 97.97 |  | 97.97 | 195.94 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 195.94 |  |  | 0
| 243 | Identification | Apply to All Pipe & Valve | LOT | 1 | 0 | 263.74 |  | 263.74 | 263.74 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 263.74 |  |  | 0
| 244 | [20 empty] | 0
| 245 | [ Sub Total ] | [7 empty] | 7303.9099 |  | 0 |  | 3175.875 |  | 3175.875 | 43.48% |  | 4128.035 |  |  | 0
| 246 | M1-4. Fire Protection Work | [19 empty] | 0
SPRINKLER SUB-MAIN, BRANCH PIPE, AND HEADOH1 (WET) SQLF | 247 | SPRINKLER SUB-MAIN, BRANCH PIPE, AND HEAD | OH1 (WET) Include Pipe fittings(Elbows, Tees, Nipples, Reducers, Caps, Flanges, etc.), obstruction, sleeves, opennings, inserts, finishings around openings or sleeves, Supports, Anti-Corrosion Paint, According to the specified pipe joining methods. | SQLF | 4998 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 4998 | 0 |  | #NAME? | #REF!
Fire Extinguisher20 LB, ABCEA | 248 | Fire Extinguisher | 20 LB, ABC DRY CHEMICAL, INCLUDE SUPPORT & SIGN | EA | 5 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 0 |  | #NAME? | #REF!
TestingAs per insL/S | 249 | Testing | As per inspection & Test report - Material inspetion / Visual / Welding inspetion / Hydro & Leak Test and etc. | L/S | 1 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 0 |  | #NAME? | #REF!
DesignWorking, sL/S | 250 | Design | Working, shop, and as-built drawings | L/S | 1 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 0 |  | #NAME? | #REF!
AHJ ApprovalsSubmissionL/S | 251 | AHJ Approvals | Submission and discussion works related with AHJ | L/S | 1 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 0 |  | #NAME? | #REF!
| 252 | [19 empty] | 0 | 0
| 253 | [ Sub Total ] | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 0% |  | 0 |  | 13367900.568 | -13367900.568
| 254 | M1-5. Mechanical Demolition Work | [19 empty] | 0
Demolition EquipmentEF-703-170EA | 255 | Demolition Equipment | EF-703-1701 (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 3465.26 |  | 3465.26 | 3465.26 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 3465.26
Demolition EquipmentEF-703-170EA | 256 | Demolition Equipment | EF-703-1702 (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 3465.26 |  | 3465.26 | 3465.26 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 3465.26
Demolition EquipmentRP-1 (InclEA | 257 | Demolition Equipment | RP-1 (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 802.47 |  | 802.47 | 802.47 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 802.47
Demolition EquipmentWH-1 (InclEA | 258 | Demolition Equipment | WH-1 (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 1386.1 |  | 1386.1 | 1386.1 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1386.1
Demolition EquipmentETWH-1 (InEA | 259 | Demolition Equipment | ETWH-1 (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 1021.34 |  | 1021.34 | 1021.34 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1021.34
Demolition EquipmentTMV-1 (IncEA | 260 | Demolition Equipment | TMV-1 (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 656.56 |  | 656.56 | 656.56 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 656.56
Demolition EquipmentFOAM WATEREA | 261 | Demolition Equipment | FOAM WATER SYSTEM TANK (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 4924.35 |  | 4924.35 | 4924.35 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 4924.35
Demolition EquipmentEMERGENCY/EA | 262 | Demolition Equipment | EMERGENCY/EYE SHOWER (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 1 | 0 | 1313.15 |  | 1313.15 | 1313.15 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1313.15
Demolition Air TerminalDamper, DiEA | 263 | Demolition Air Terminal | Damper, Diffuser, Grille, Reister etc (Includes all associated ducts, piping, dampers, valves, insulation, fittings, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | EA | 3 | 0 | 145.9 |  | 145.9 | 437.7 |  | 0 |  | 0 | 0 | 0 | 0% | 3 | 437.7
Demolition PipeGalva BlacM | 264 | Demolition Pipe | Galva Black Steel, Stainless Steel, CPVC, PVC etc (Includes all associated ducts, piping, dampers, valves, insulation, fittings, end cap installation, supports, hangers, foundations, removal from site, transportation, and disposal etc.) | M | 276.7 | 0 | 31.77 |  | 31.77 | 8790.759 |  | 0 |  | 0 | 0 | 0 | 0% | 276.7 | 8790.759
| 265 | [19 empty] | 0 | 0
| 266 | [ Sub Total ] | [7 empty] | 26262.949 |  | 0 |  | 0 |  | 0 | 0% |  | 26262.949 |  | 12515235.9496 | -12515235.9496
| 267 | M1-6. Civil WORK | [19 empty] | 0
| 268 | Demolition Work | [6 empty] | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 269 | Demolition of PVC Pipe (Ø3") | with Cleanout | EA | 21 | 0 | 1038.12 |  | 1038.12 | 21800.52 |  | 0 |  | 0 | 0 | 0 | 0% | 21 | 21800.52 |  | 0 | 0
| 270 | Re-Installation Work (Pipe) |  |  |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 271 | Installation of PVC Pipe (SDR 26 PVC Pipe Ø6") | Pipe : PVC Φ 6"/ Max 8" thick Compacted lifts, 98% dry density Inc. Angle Part | LF | 406 | 0 | 145.94 |  | 145.94 | 59251.64 |  | 0 |  | 0 | 0 | 0 | 0% | 406 | 59251.64 |  | 0 | 0
| 272 | Installation of Cleanout (Ø6") | Type : SDR 26 PVC, Diameter = Ø6" | EA | 1 | 0 | 2870.17 |  | 2870.17 | 2870.17 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2870.17 |  | 0 | 0
| 273 | Connect to existing Pipe |  | EA | 2 | 0 | 6541.24 |  | 6541.24 | 13082.48 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 13082.48 |  | 0 | 0
| 274 | Grease Waste Management |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 275 | Installation work |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 63667.8 | -63667.8
| 276 | Installation of PVC Pipe (SDR 26 PVC Pipe Ø4") | Pipe : PVC Φ 4"/ Max 8" thick Compacted lifts, 98% dry density | LF | 90 | 0 | 123.07 |  | 123.07 | 11076.3 |  | 0 |  | 0 | 0 | 0 | 0% | 90 | 11076.3 |  | 0 | 0
| 277 | Installation of Cleanout (Ø4") | Type : SDR 26 PVC, Diameter = Ø4" | EA | 1 | 0 | 2188.77 |  | 2188.77 | 2188.77 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2188.77 |  | 0 | 0
| 278 | Installation of Sanitary Sewer M/H (Ø48") |  | EA | 1 | 0 | 26089.03 | 0 | 26089.03 | 26089.03 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 26089.03 |  | 0 | 0
| 279 | Secondary Containment System |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 280 | Demolition Work |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 281 | Demolition of PVC Pipe (Ø10") | with Cleanout | EA | 1 | 0 | 9518.81 | 0 | 9518.81 | 9518.81 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 9518.81 |  | 0 | 0
| 282 | Demolition of DIP Pipe (Ø8") |  | EA | 1 | 0 | 14526.41 |  | 14526.41 | 14526.41 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 14526.41 |  | 0 | 0
| 283 | Demolition of Greenvalve&M/H (Ø8"/Ø48") |  | EA | 1 | 0 | 20452.14 |  | 20452.14 | 20452.14 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 20452.14 |  | 0 | 0
| 284 | Pit Backfilling Work |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 285 | Installation of Plug | Blocking the pipe in both directions at the pit | EA | 2 | 0 | 3155.29 |  | 3155.29 | 6310.58 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 6310.58 |  | 0 | 0
| 286 | Capacith |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
| 287 | Installation work |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 0 | 0 |  | 63667.8 | -63667.8
| 288 | Pipe installation by Directional Boring | Pipe Diameter Φ = 4" | LF | 100 | 0 | 334.94 |  | 334.94 | 33494 |  | 0 |  | 0 | 0 | 0 | 0% | 100 | 33494 |  | 0 | 0
| 289 | Installation of Water Angle | CW PVC SDR-21, Ø4", 90˚ | EA | 1 | 0 | 1904.68 |  | 1904.68 | 1904.68 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 1904.68 |  | 0 | 0
| 290 | Installation of Water Tee | CW PVC SDR-21, 4"x4"x4" | EA | 1 | 0 | 2259.06 |  | 2259.06 | 2259.06 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 2259.06 |  | 0 | 0
| 291 | Installation of Gatevalve | Type = CW PVD SDR-21, Ø4" | EA | 2 | 0 | 3897.23 |  | 3897.23 | 7794.46 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 7794.46 |  | 0 | 0
| 292 | Installation of Gatevalve M/H | Size = Ø48" | EA | 2 | 0 | 15075.6 |  | 15075.6 | 30151.2 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 30151.2 |  | 0 | 0
| 293 | Installation of PVC Pipe (CW PVC SDR-21) | Pipe : PVC Φ 4"/ Max 8" thick Compacted lifts, 98% dry density | LF | 154 | 0 | 159.88 |  | 159.88 | 24621.52 |  | 0 |  | 0 | 0 | 0 | 0% | 154 | 24621.52 |  | 0 | 0
| 294 | Connect to existing pipe | Inc. Megalug | EA | 2 | 0 | 6794.95 |  | 6794.95 | 13589.9 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 13589.9 |  | 0 | 0
| 295 | [19 empty] | 0 | 0
| 296 | [ Sub Total ] | [7 empty] | 300981.67 |  | 0 |  | 0 |  | 0 | 0% |  | 300981.67 |  | 63667.8 | -63667.8
| 297 | [ 설비공사 Total ] | [7 empty] | 571271.3811 |  | 0 |  | 17851.5016 |  | 17851.5016 | 3.125% |  | 553419.8795 |  | 63667.8 | -63667.8
| 298 | 전기공사 | [19 empty] | 0
| 299 | 01. POWER DISTRIBUTION WORK | [19 empty] | 0
Distribution Panel (Kitchen-Main)3P4W 208-1SET | 300 | Distribution Panel (Kitchen-Main) | 3P4W 208-120V 400AF/400AT | SET | 2 | 4517.2 | 3052.88 |  | 7570.08 | 15140.16 |  | 0 | 1.6 | 12112.128 | 1.6 | 12112.128 | 80% | 0.4 | 3028.032
Distribution Panel (Kitchen-01-1,2)3P 480V 40SET | 301 | Distribution Panel (Kitchen-01-1,2) | 3P 480V 400AF/400AT | SET | 2 | 4141.69 | 2822.79 |  | 6964.48 | 13928.96 |  | 0 | 1.6 | 11143.168 | 1.6 | 11143.168 | 80% | 0.4 | 2785.792
Distribution Panel (Kitchen-02-1)3P4W 480-2SET | 302 | Distribution Panel (Kitchen-02-1) | 3P4W 480-277V 150AF/125AT | SET | 1 | 2253.08 | 2008.53 |  | 4261.61 | 4261.61 |  | 0 | 0.8 | 3409.288 | 0.8 | 3409.288 | 80% | 0.2 | 852.322
Distribution Panel (Kitchen-02-2)3P4W 208-1SET | 303 | Distribution Panel (Kitchen-02-2) | 3P4W 208-120V 150AF/125AT | SET | 1 | 2038.51 | 2008.53 |  | 4047.04 | 4047.04 |  | 0 | 0.8 | 3237.632 | 0.8 | 3237.632 | 80% | 0.2 | 809.408
Dry Transformer (Kitchen-01-2(DTR))480/208V-1EA | 304 | Dry Transformer (Kitchen-01-2(DTR)) | 480/208V-120V 150kVA | EA | 2 | 4086 | 2822.79 |  | 6908.79 | 13817.58 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 13817.58
PANEL SUPPORTUnistrut /SET | 305 | PANEL SUPPORT | Unistrut / corner angle / bolt & nut / anchor for concrete … etc | SET | 6 | 150.19 | 447.89 |  | 598.08 | 3588.48 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 3588.48
ALUMINUM CABLE TRAY (LADDER TYPE)12"Width, LF | 306 | ALUMINUM CABLE TRAY (LADDER TYPE) | 12"Width, 4"height, 9"rung spacing | LF | 160 | 9.66 | 18.34 |  | 28 | 4480 |  | 0 | 48 | 1344 | 48 | 1344 | 30% | 112 | 3136
ALUMINUM CABLE TRAY (LADDER TYPE)24"Width, LF | 307 | ALUMINUM CABLE TRAY (LADDER TYPE) | 24"Width, 4"height, 9"rung spacing | LF | 230 | 13.94 | 21.22 |  | 35.16 | 8086.8 |  | 0 | 69 | 2426.04 | 69 | 2426.04 | 30% | 161 | 5660.76
ALUMINUM CABLE TRAY (LADDER TYPE)36"Width, LF | 308 | ALUMINUM CABLE TRAY (LADDER TYPE) | 36"Width, 4"height, 9"rung spacing | LF | 108 | 18.23 | 24.1 |  | 42.33 | 4571.64 |  | 0 | 32.4 | 1371.492 | 32.4 | 1371.492 | 30% | 75.6 | 3200.148 |  | 7786.2 | -7786.2
ALUMINUM HORIZONTAL ELBOW (LADDER TYPE)24"Width, EA | 309 | ALUMINUM HORIZONTAL ELBOW (LADDER TYPE) | 24"Width, 4"height, 9"rung spacing | EA | 1 | 171.66 | 155 |  | 326.66 | 326.66 |  | 0 | 0.3 | 97.998 | 0.3 | 97.998 | 30% | 0.7 | 228.662
ALUMINUM HORIZONTAL ELBOW (LADDER TYPE)36"Width, EA | 310 | ALUMINUM HORIZONTAL ELBOW (LADDER TYPE) | 36"Width, 4"height, 9"rung spacing | EA | 1 | 225.29 | 178.02 |  | 403.31 | 403.31 |  | 0 | 0.3 | 120.993 | 0.3 | 120.993 | 30% | 0.7 | 282.317 |  | 13349.448 | -13349.448
ALUMINUM VERTICAL ELBOW (LADDER TYPE)12"Width, EA | 311 | ALUMINUM VERTICAL ELBOW (LADDER TYPE) | 12"Width, 4"height, 9"rung spacing | EA | 8 | 83.69 | 128.61 |  | 212.3 | 1698.4 |  | 0 | 2.4 | 509.52 | 2.4 | 509.52 | 30% | 5.6 | 1188.88 |  | 0 | 0
ALUMINUM VERTICAL ELBOW (LADDER TYPE)24"Width, 4"height, 9"rung spacingEA | 312 | ALUMINUM VERTICAL ELBOW (LADDER TYPE) | 24"Width, 4"height, 9"rung spacing | EA | 6 | 124.48 | 155 |  | 279.48 | 1676.88 |  | 0 | 1.8 | 503.064 | 1.8 | 503.064 | 30% | 4.2 | 1173.816 |  | 0 | 0
ALUMINUM VERTICAL ELBOW (LADDER TYPE)36"Width, 4"height, 9"rung spacingEA | 313 | ALUMINUM VERTICAL ELBOW (LADDER TYPE) | 36"Width, 4"height, 9"rung spacing | EA | 4 | 183.49 | 178.02 |  | 361.51 | 1446.04 |  | 0 | 1.2 | 433.812 | 1.2 | 433.812 | 30% | 2.8 | 1012.228 |  | 0 | 0
ALUMINUM TEE HORIZONTAL (LADDER TYPE)24"Width, 4"height, 9"rung spacingEA | 314 | ALUMINUM TEE HORIZONTAL (LADDER TYPE) | 24"Width, 4"height, 9"rung spacing | EA | 1 | 83.69 | 128.61 |  | 212.3 | 212.3 |  | 0 | 0.3 | 63.69 | 0.3 | 63.69 | 30% | 0.7 | 148.61 |  | 0 | 0
12" Cable tray support W/Accessories12" Width including beam clamp, square washer, unistrut, 2 rods, etcSET | 315 | 12" Cable tray support W/Accessories | 12" Width including beam clamp, square washer, unistrut, 2 rods, etc | SET | 24 | 29.5 | 83.81 |  | 113.31 | 2719.44 |  | 0 | 7.2 | 815.832 | 7.2 | 815.832 | 30% | 16.8 | 1903.608 |  | 0 | 0
24" Cable tray support W/Accessories24" Width including beam clamp, square washer, unistrut, 2 rods, etcSET | 316 | 24" Cable tray support W/Accessories | 24" Width including beam clamp, square washer, unistrut, 2 rods, etc | SET | 21 | 40.23 | 96.46 |  | 136.69 | 2870.49 |  | 0 | 6.3 | 861.147 | 6.3 | 861.147 | 30% | 14.7 | 2009.343 |  | 0 | 0
36" Cable tray support W/Accessories36" Width including beam clamp, square washer, unistrut, 2 rods, etcSET | 317 | 36" Cable tray support W/Accessories | 36" Width including beam clamp, square washer, unistrut, 2 rods, etc | SET | 15 | 50.96 | 109.1 |  | 160.06 | 2400.9 |  | 0 | 4.5 | 720.27 | 4.5 | 720.27 | 30% | 10.5 | 1680.63
CABLE TRAY BOX CONNECTOR12", Bolt, Nut, ETCSET | 318 | CABLE TRAY BOX CONNECTOR | 12", Bolt, Nut, ETC | SET | 2 | 13.41 | 32.15 |  | 45.56 | 91.12 |  | 0 | 0.6 | 27.336 | 0.6 | 27.336 | 30% | 1.4 | 63.784
CABLE TRAY BOX CONNECTOR24", Bolt, Nut, ETCSET | 319 | CABLE TRAY BOX CONNECTOR | 24", Bolt, Nut, ETC | SET | 23 | 18.77 | 39.03 |  | 57.8 | 1329.4 |  | 0 | 6.9 | 398.82 | 6.9 | 398.82 | 30% | 16.1 | 930.58
CABLE TRAY BOX CONNECTOR36", Bolt, Nut, ETCSET | 320 | CABLE TRAY BOX CONNECTOR | 36", Bolt, Nut, ETC | SET | 2 | 24.13 | 45.92 |  | 70.05 | 140.1 |  | 0 | 0.6 | 42.03 | 0.6 | 42.03 | 30% | 1.4 | 98.07
BONDING JUMPER12"EA | 321 | BONDING JUMPER | 12" | EA | 63 | 6.43 | 22.96 |  | 29.39 | 1851.57 |  | 0 |  | 0 | 0 | 0 | 0% | 63 | 1851.57
ELECTRICAL METALLIC TUBING (EMT)3" SET SCREWLF | 322 | ELECTRICAL METALLIC TUBING (EMT) | 3" SET SCREW | LF | 130 | 5.08 | 14.3 |  | 19.38 | 2519.4 |  | 0 |  | 0 | 0 | 0 | 0% | 130 | 2519.4
ELECTRICAL METALLIC TUBING (EMT)2" SET SCREWLF | 323 | ELECTRICAL METALLIC TUBING (EMT) | 2" SET SCREW | LF | 400 | 2.78 | 10.28 |  | 13.06 | 5224 |  | 0 |  | 0 | 0 | 0 | 0% | 400 | 5224
ELECTRICAL METALLIC TUBING (EMT)1-1/2" SET SCREWLF | 324 | ELECTRICAL METALLIC TUBING (EMT) | 1-1/2" SET SCREW | LF | 160 | 2.03 | 9.05 |  | 11.08 | 1772.8 |  | 0 |  | 0 | 0 | 0 | 0% | 160 | 1772.8
ELECTRICAL METALLIC TUBING (EMT)1" SET SCREWLF | 325 | ELECTRICAL METALLIC TUBING (EMT) | 1" SET SCREW | LF | 100 | 1.17 | 7.1 |  | 8.27 | 827 |  | 0 |  | 0 | 0 | 0 | 0% | 100 | 827
CONDUIT SUPPORT SYSTEM3"SET | 326 | CONDUIT SUPPORT SYSTEM | 3" | SET | 26 | 15 | 41.33 |  | 56.33 | 1464.58 |  | 0 |  | 0 | 0 | 0 | 0% | 26 | 1464.58
CONDUIT SUPPORT SYSTEM2"SET | 327 | CONDUIT SUPPORT SYSTEM | 2" | SET | 80 | 9.66 | 33.3 |  | 42.96 | 3436.8 |  | 0 |  | 0 | 0 | 0 | 0% | 80 | 3436.8
CONDUIT SUPPORT SYSTEM1-1/2"SET | 328 | CONDUIT SUPPORT SYSTEM | 1-1/2" | SET | 32 | 8.04 | 30.99 |  | 39.03 | 1248.96 |  | 0 |  | 0 | 0 | 0 | 0% | 32 | 1248.96
CONDUIT SUPPORT SYSTEM1"SET | 329 | CONDUIT SUPPORT SYSTEM | 1" | SET | 20 | 6.43 | 28.14 |  | 34.57 | 691.4 |  | 0 |  | 0 | 0 | 0 | 0% | 20 | 691.4
Liquidtight Flexible Metal Conduit3"LF | 330 | Liquidtight Flexible Metal Conduit | 3" | LF | 20 | 7.5 | 11.7 |  | 19.2 | 384 |  | 0 |  | 0 | 0 | 0 | 0% | 20 | 384
Liquidtight Flexible Metal Conduit2"LF | 331 | Liquidtight Flexible Metal Conduit | 2" | LF | 50 | 4.28 | 9.15 |  | 13.43 | 671.5 |  | 0 |  | 0 | 0 | 0 | 0% | 50 | 671.5
Liquidtight Flexible Metal Conduit1-1/2"LF | 332 | Liquidtight Flexible Metal Conduit | 1-1/2" | LF | 20 | 3.48 | 8.32 |  | 11.8 | 236 |  | 0 |  | 0 | 0 | 0 | 0% | 20 | 236
Liquidtight Flexible Metal Conduit1"LF | 333 | Liquidtight Flexible Metal Conduit | 1" | LF | 10 | 2.24 | 7.1 |  | 9.34 | 93.4 |  | 0 |  | 0 | 0 | 0 | 0% | 10 | 93.4
Liquidtight Flexible Metal Conduit Connector3"EA | 334 | Liquidtight Flexible Metal Conduit Connector | 3" | EA | 2 | 20.37 | 22.96 |  | 43.33 | 86.66 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 86.66
Liquidtight Flexible Metal Conduit Connector2"EA | 335 | Liquidtight Flexible Metal Conduit Connector | 2" | EA | 5 | 11.79 | 18.34 |  | 30.13 | 150.65 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 150.65 |  | 7786.2 | -7786.2
Liquidtight Flexible Metal Conduit Connector1-1/2"EA | 336 | Liquidtight Flexible Metal Conduit Connector | 1-1/2" | EA | 2 | 8.57 | 15.46 |  | 24.03 | 48.06 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 48.06
Liquidtight Flexible Metal Conduit Connector1"EA | 337 | Liquidtight Flexible Metal Conduit Connector | 1" | EA | 1 | 5.89 | 12.6 |  | 18.49 | 18.49 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 18.49 |  | 13349.448 | -13349.448
Grounding Bushing3"EA | 338 | Grounding Bushing | 3" | EA | 2 | 12.86 | 19.5 |  | 32.36 | 64.72 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 64.72 |  | 0 | 0
Grounding Bushing2"EA | 339 | Grounding Bushing | 2" | EA | 5 | 7.5 | 15.46 |  | 22.96 | 114.8 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 114.8 |  | 0 | 0
Grounding Bushing1-1/2"EA | 340 | Grounding Bushing | 1-1/2" | EA | 8 | 5.89 | 12.85 |  | 18.74 | 149.92 |  | 0 |  | 0 | 0 | 0 | 0% | 8 | 149.92 |  | 0 | 0
Grounding Bushing1"EA | 341 | Grounding Bushing | 1" | EA | 8 | 4.28 | 11.45 |  | 15.73 | 125.84 |  | 0 |  | 0 | 0 | 0 | 0% | 8 | 125.84 |  | 0 | 0
SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED500kcmilLF | 342 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | 500kcmil | LF | 744 | 7.23 | 5.83 |  | 13.06 | 9716.64 |  | 0 | 744 | 9716.64 | 744 | 9716.64 | 100% | 0 | 0 |  | 0 | 0
SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED250kcmilLF | 343 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | 250kcmil | LF | 1347 | 3.85 | 4.17 |  | 8.02 | 10802.94 |  | 0 | 1347 | 10802.94 | 1347 | 10802.94 | 100% | 0 | 0 |  | 0 | 0
SINGLE CONDUCTOR (THHN/THWN-2) - STRANDEDAWG#3/0LF | 344 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | AWG#3/0 | LF | 264 | 2.19 | 3.13 |  | 5.32 | 1404.48 |  | 0 | 264 | 1404.48 | 264 | 1404.48 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN-2) - STRANDEDAWG#1/0LF | 345 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | AWG#1/0 | LF | 352 | 1.7 | 2.84 |  | 4.54 | 1598.08 |  | 0 | 352 | 1598.08 | 352 | 1598.08 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN-2) - STRANDEDAWG#1LF | 346 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | AWG#1 | LF | 352 | 1.43 | 2.6 |  | 4.03 | 1418.56 |  | 0 | 352 | 1418.56 | 352 | 1418.56 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN-2) - STRANDEDAWG#6LF | 347 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | AWG#6 | LF | 500 | 0.58 | 1.53 |  | 2.11 | 1055 |  | 0 | 500 | 1055 | 500 | 1055 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN) - STRANDEDAWG#2, GroundLF | 348 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#2, Ground | LF | 572 | 1.17 | 2.35 |  | 3.52 | 2013.44 |  | 0 | 572 | 2013.44 | 572 | 2013.44 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN) - STRANDEDAWG#4, GroundLF | 349 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#4, Ground | LF | 88 | 0.79 | 1.92 |  | 2.71 | 238.48 |  | 0 | 88 | 238.48 | 88 | 238.48 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN) - STRANDEDAWG#6, GroundLF | 350 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#6, Ground | LF | 176 | 0.58 | 1.53 |  | 2.11 | 371.36 |  | 0 | 176 | 371.36 | 176 | 371.36 | 100% | 0 | 0
SINGLE CONDUCTOR (THHN/THWN) - STRANDEDAWG#8, GroundLF | 351 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#8, Ground | LF | 60 | 0.39 | 1.42 |  | 1.81 | 108.6 |  | 0 | 60 | 108.6 | 60 | 108.6 | 100% | 0 | 0
CONNECTION AND TERMINATION#500 Kcmil COMPRESSION TYPEEA | 352 | CONNECTION AND TERMINATION | #500 Kcmil COMPRESSION TYPE | EA | 12 | 24.13 | 83.81 |  | 107.94 | 1295.28 |  | 0 |  | 0 | 0 | 0 | 0% | 12 | 1295.28
CONNECTION AND TERMINATION#250 Kcmil COMPRESSION TYPEEA | 353 | CONNECTION AND TERMINATION | #250 Kcmil COMPRESSION TYPE | EA | 6 | 17.16 | 61.97 |  | 79.13 | 474.78 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 474.78
CONNECTION AND TERMINATIONAWG#3/0 COMPRESSION TYPEEA | 354 | CONNECTION AND TERMINATION | AWG#3/0 COMPRESSION TYPE | EA | 12 | 11.79 | 44.78 |  | 56.57 | 678.84 |  | 0 |  | 0 | 0 | 0 | 0% | 12 | 678.84
CONNECTION AND TERMINATIONAWG#1/0 COMPRESSION TYPEEA | 355 | CONNECTION AND TERMINATION | AWG#1/0 COMPRESSION TYPE | EA | 16 | 9.66 | 39.03 |  | 48.69 | 779.04 |  | 0 |  | 0 | 0 | 0 | 0% | 16 | 779.04
CONNECTION AND TERMINATIONAWG#1 COMPRESSION TYPEEA | 356 | CONNECTION AND TERMINATION | AWG#1 COMPRESSION TYPE | EA | 16 | 8.04 | 33.3 |  | 41.34 | 661.44 |  | 0 |  | 0 | 0 | 0 | 0% | 16 | 661.44
CONNECTION AND TERMINATIONAWG#2 COMPRESSION TYPEEA | 357 | CONNECTION AND TERMINATION | AWG#2 COMPRESSION TYPE | EA | 2 | 6.97 | 28.7 |  | 35.67 | 71.34 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 71.34
CONNECTION AND TERMINATIONAWG#4 COMPRESSION TYPEEA | 358 | CONNECTION AND TERMINATION | AWG#4 COMPRESSION TYPE | EA | 4 | 5.89 | 25.84 |  | 31.73 | 126.92 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 126.92
CONNECTION AND TERMINATIONAWG#6 COMPRESSION TYPEEA | 359 | CONNECTION AND TERMINATION | AWG#6 COMPRESSION TYPE | EA | 20 | 4.82 | 22.96 |  | 27.78 | 555.6 |  | 0 |  | 0 | 0 | 0 | 0% | 20 | 555.6 |  | 0 | 0
CONNECTION AND TERMINATIONAWG#8 COMPRESSION TYPEEA | 360 | CONNECTION AND TERMINATION | AWG#8 COMPRESSION TYPE | EA | 4 | 4.28 | 19.5 |  | 23.78 | 95.12 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 95.12
JUNCTION BOX, NEMA-112"W x 12"H x 6"DEA | 361 | JUNCTION BOX, NEMA-1 | 12"W x 12"H x 6"D | EA | 4 | 45.6 | 120.61 |  | 166.21 | 664.84 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 664.84
JUNCTION BOX, NEMA-124"W x 24"H x 12"DEA | 362 | JUNCTION BOX, NEMA-1 | 24"W x 24"H x 12"D | EA | 2 | 139.48 | 229.7 |  | 369.18 | 738.36 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 738.36
FIRE BLOCK SEALANT (RED)12 OZEA | 363 | FIRE BLOCK SEALANT (RED) | 12 OZ | EA | 10 | 15 | 44.78 |  | 59.78 | 597.8 |  | 0 |  | 0 | 0 | 0 | 0% | 10 | 597.8 |  | 3822.15 | -3822.15
FIRE STOP BARRIER36"Width x 4"HeightSET | 364 | FIRE STOP BARRIER | 36"Width x 4"Height | SET | 2 | 128.74 | 229.7 |  | 358.44 | 716.88 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 716.88
FIRE STOP BARRIER24"Width x 4"HeightSET | 365 | FIRE STOP BARRIER | 24"Width x 4"Height | SET | 2 | 101.91 | 192.92 |  | 294.83 | 589.66 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 589.66
Trenching And Backfill (W/Compaction)3' WIDE X 5' DEEPLF | 366 | Trenching And Backfill (W/Compaction) | 3' WIDE X 5' DEEP | LF | 10 | 4.28 | 97 |  | 101.28 | 1012.8 |  | 0 |  | 0 | 0 | 0 | 0% | 10 | 1012.8
| 367 | [19 empty] | 0 | 0
| 368 | [ Sub Total ] | [7 empty] | 146204.14 |  | 0 |  | 68365.84 |  | 68365.84 | 46.76% |  | 77838.3 |  | 347280.1577 | -347280.1577
| 369 | 02. MECHANICAL POWER WORK | [19 empty] | 0
| 370 | Disconnect SW | 480V 3P 30A NEMA-1 | EA | 15 | 139.48 | 281.37 |  | 420.85 | 6312.75 |  | 0 |  | 0 | 0 | 0 | 0% | 15 | 6312.75
| 371 | Disconnect SW | 480V 3P 60A NEMA-1 | EA | 5 | 225.29 | 356.06 |  | 581.35 | 2906.75 |  | 0 |  | 0 | 0 | 0 | 0% | 5 | 2906.75
| 372 | Disconnect SW | 480V 3P 200A NEMA-1 | EA | 4 | 434.66 | 546.68 |  | 981.34 | 3925.36 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 3925.36
| 373 | ELECTRICAL METALLIC TUBING (EMT) | 2" SET SCREW | LF | 550 | 2.78 | 10.28 |  | 13.06 | 7183 |  | 0 |  | 0 | 0 | 0 | 0% | 550 | 7183
| 374 | ELECTRICAL METALLIC TUBING (EMT) | 1-1/2" SET SCREW | LF | 550 | 2.03 | 9.05 |  | 11.08 | 6094 |  | 0 |  | 0 | 0 | 0 | 0% | 550 | 6094
| 375 | ELECTRICAL METALLIC TUBING (EMT) | 1" SET SCREW | LF | 1100 | 1.17 | 7.1 |  | 8.27 | 9097 |  | 0 |  | 0 | 0 | 0 | 0% | 1100 | 9097
| 376 | ELECTRICAL METALLIC TUBING (EMT) | 3/4" SET SCREW | LF | 2250 | 0.85 | 6.18 |  | 7.03 | 15817.5 |  | 0 |  | 0 | 0 | 0 | 0% | 2250 | 15817.5
| 377 | CONDUIT SUPPORT SYSTEM | 2" | SET | 110 | 9.66 | 33.3 |  | 42.96 | 4725.6 |  | 0 |  | 0 | 0 | 0 | 0% | 110 | 4725.6 |  | 0 | 0
| 378 | CONDUIT SUPPORT SYSTEM | 1-1/2" | SET | 110 | 8.04 | 30.99 |  | 39.03 | 4293.3 |  | 0 |  | 0 | 0 | 0 | 0% | 110 | 4293.3
| 379 | CONDUIT SUPPORT SYSTEM | 1" | SET | 220 | 6.43 | 28.14 |  | 34.57 | 7605.4 |  | 0 |  | 0 | 0 | 0 | 0% | 220 | 7605.4
| 380 | CONDUIT SUPPORT SYSTEM | 3/4" | SET | 450 | 5.36 | 25.24 |  | 30.6 | 13770 |  | 0 |  | 0 | 0 | 0 | 0% | 450 | 13770
| 381 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | AWG#1/0 | LF | 372 | 1.7 | 2.84 |  | 4.54 | 1688.88 |  | 0 |  | 0 | 0 | 0 | 0% | 372 | 1688.88
| 382 | SINGLE CONDUCTOR (THHN/THWN-2) - STRANDED | AWG#6 | LF | 3720 | 0.58 | 1.53 |  | 2.11 | 7849.2 |  | 0 |  | 0 | 0 | 0 | 0% | 3720 | 7849.2
| 383 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#6, Ground | LF | 124 | 0.58 | 1.53 |  | 2.11 | 261.64 |  | 0 |  | 0 | 0 | 0 | 0% | 124 | 261.64
| 384 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#8, Ground | LF | 6700 | 0.39 | 1.42 |  | 1.81 | 12127 |  | 0 |  | 0 | 0 | 0 | 0% | 6700 | 12127
| 385 | Multi Conductor (THHN/THWN-2) - Stranded | (3PH) AWG#8 | LF | 1340 | 2.89 | 3.38 |  | 6.27 | 8401.8 |  | 0 |  | 0 | 0 | 0 | 0% | 1340 | 8401.8
| 386 | Multi Conductor (THHN/THWN-2) - Stranded | (3PH) AWG#10 | LF | 4050 | 1.92 | 2.84 |  | 4.76 | 19278 |  | 0 |  | 0 | 0 | 0 | 0% | 4050 | 19278
| 387 | CONNECTION AND TERMINATION | AWG#1/0 COMPRESSION TYPE | EA | 6 | 9.66 | 39.03 |  | 48.69 | 292.14 |  | 0 |  | 0 | 0 | 0 | 0% | 6 | 292.14 |  | 11752.6845 | -11752.6845
| 388 | CONNECTION AND TERMINATION | AWG#6 COMPRESSION TYPE | EA | 60 | 4.82 | 22.96 |  | 27.78 | 1666.8 |  | 0 |  | 0 | 0 | 0 | 0% | 60 | 1666.8 |  | 23858.932 | -23858.932
| 389 | CONNECTION AND TERMINATION | AWG#8 COMPRESSION TYPE | EA | 120 | 4.28 | 19.5 |  | 23.78 | 2853.6 |  | 0 |  | 0 | 0 | 0 | 0% | 120 | 2853.6
| 390 | CONNECTION AND TERMINATION | AWG#10 COMPRESSION TYPE | EA | 60 | 3.74 | 14.88 |  | 18.62 | 1117.2 |  | 0 |  | 0 | 0 | 0 | 0% | 60 | 1117.2
| 391 | JUNCTION BOX, NEMA-1 | 4"W x 4"H x 2-1/4"D | EA | 40 | 9.66 | 44.78 |  | 54.44 | 2177.6 |  | 0 |  | 0 | 0 | 0 | 0% | 40 | 2177.6
| 392 | JUNCTION BOX, NEMA-1 | 8"W x 8"H x 2-1/4"D | EA | 8 | 29.5 | 82.68 |  | 112.18 | 897.44 |  | 0 |  | 0 | 0 | 0 | 0% | 8 | 897.44 |  | 0 | 0
| 393 | MOTER SWITCH | 480V 30A 3P | EA | 1 | 96.55 | 155 |  | 251.55 | 251.55 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 251.55
| 394 | MOTER SWITCH | 480V 60A 3P | EA | 1 | 171.66 | 206.69 |  | 378.35 | 378.35 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 378.35
| 395 | [19 empty] | 0 | 0
| 396 | [ Sub Total ] | [7 empty] | 140971.86 |  | 0 |  | 0 |  | 0 | 0% |  | 140971.86 |  | 706239.6013 | -706239.6013
| 397 | 03. Lighting WORK | [19 empty] | 0
ELECTRICAL METALLIC TUBING (EMT)3/4" SET SLF | 398 | ELECTRICAL METALLIC TUBING (EMT) | 3/4" SET SCREW | LF | 1500 | 0.85 | 6.18 |  | 7.03 | 10545 |  | 0 |  | 0 | 0 | 0 | 0% | 1500 | 10545 |  | 0 | 0
CONDUIT SUPPORT SYSTEM3/4"SET | 399 | CONDUIT SUPPORT SYSTEM | 3/4" | SET | 150 | 5.36 | 25.24 |  | 30.6 | 4590 |  | 0 |  | 0 | 0 | 0 | 0% | 150 | 4590 |  | 1008.288 | -1008.288
SINGLE CONDUCTOR (THHN/THWN) - STRANDEDAWG#12LF | 400 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#12 | LF | 525 | 0.28 | 1.27 |  | 1.55 | 813.75 |  | 0 |  | 0 | 0 | 0 | 0% | 525 | 813.75 |  | 3418.578 | -3418.578
Multi Conductor (THHN/THWN) - Stranded(3PH) AWG#LF | 401 | Multi Conductor (THHN/THWN) - Stranded | (3PH) AWG#12 | LF | 675 | 0.89 | 1.92 |  | 2.81 | 1896.75 |  | 0 |  | 0 | 0 | 0 | 0% | 675 | 1896.75 |  | 0 | 0
MC(FLEXIBLE ALUMIUM CONDUIT) CABLE(3PH) AWG#LF | 402 | MC(FLEXIBLE ALUMIUM CONDUIT) CABLE | (3PH) AWG#12 | LF | 1000 | 1.39 | 2.54 |  | 3.93 | 3930 |  | 0 |  | 0 | 0 | 0 | 0% | 1000 | 3930 |  | 0 | 0
MC CABLE HANGER CLAMP14-2 TO 10EA | 403 | MC CABLE HANGER CLAMP | 14-2 TO 10-3 MC | EA | 125 | 3.2 | 17.78 |  | 20.98 | 2622.5 |  | 0 |  | 0 | 0 | 0 | 0% | 125 | 2622.5 |  | 0 | 0
Metal Clad Cable(M/C) FittingBusing,WirEA | 404 | Metal Clad Cable(M/C) Fitting | Busing,Wirng nuts,Wire & etc | EA | 100 | 4.28 | 15.46 |  | 19.74 | 1974 |  | 0 |  | 0 | 0 | 0 | 0% | 100 | 1974 |  | 19691.1312 | -19691.1312
CONNECTION AND TERMINATIONAWG#12 COMEA | 405 | CONNECTION AND TERMINATION | AWG#12 COMPRESSION TYPE | EA | 366 | 2.14 | 11.45 |  | 13.59 | 4973.94 |  | 0 |  | 0 | 0 | 0 | 0% | 366 | 4973.94 |  | 107637.2425 | -107637.2425
JUNCTION BOX, NEMA-14"W x 2"H EA | 406 | JUNCTION BOX, NEMA-1 | 4"W x 2"H x 2-1/4"D | EA | 180 | 6.43 | 35.58 |  | 42.01 | 7561.8 |  | 0 |  | 0 | 0 | 0 | 0% | 180 | 7561.8 |  | 68821.86 | -68821.86
JUNCTION BOX, NEMA-18"W x 8"H EA | 407 | JUNCTION BOX, NEMA-1 | 8"W x 8"H x 2-1/4"D | EA | 4 | 29.5 | 82.68 |  | 112.18 | 448.72 |  | 0 |  | 0 | 0 | 0 | 0% | 4 | 448.72 |  | 0 | 0
SWITCH 1P20A 120-27EA | 408 | SWITCH 1P | 20A 120-277V 1G | EA | 13 | 17.16 | 57.44 |  | 74.6 | 969.8 |  | 0 |  | 0 | 0 | 0 | 0% | 13 | 969.8
LED Lighting FixtureTYPE "DownEA | 409 | LED Lighting Fixture | TYPE "Down Light" (LED 18.5W) | EA | 103 | 0 | 109.1 |  | 109.1 | 11237.3 |  | 0 |  | 0 | 0 | 0 | 0% | 103 | 11237.3
LED Lighting FixtureTYPE "DownEA | 410 | LED Lighting Fixture | TYPE "Down Light with Battery" | EA | 16 | 139.48 | 120.61 |  | 260.09 | 4161.44 |  | 0 |  | 0 | 0 | 0 | 0% | 16 | 4161.44 |  | 0 | 0
LED Lighting FixtureTYPE "EL"EA | 411 | LED Lighting Fixture | TYPE "EL" | EA | 11 | 118.01 | 114.85 |  | 232.86 | 2561.46 |  | 0 |  | 0 | 0 | 0 | 0% | 11 | 2561.46
LED Lighting FixtureTYPE "J1" EA | 412 | LED Lighting Fixture | TYPE "J1" (LED 3.6W)_EXIT LIGHT(W/BUG EYE) | EA | 19 | 88.5 | 95.33 |  | 183.83 | 3492.77 |  | 0 |  | 0 | 0 | 0 | 0% | 19 | 3492.77
LIGHTING SUPPORTEA | 413 | LIGHTING SUPPORT |  | EA | 19 | 24.13 | 70.04 |  | 94.17 | 1789.23 |  | 0 |  | 0 | 0 | 0 | 0% | 19 | 1789.23
| 414 | [19 empty] | 0 | 0
| 415 | [ Sub Total ] | [7 empty] | 63568.46 |  | 0 |  | 0 |  | 0 | 0% |  | 63568.46 |  | 1301271.4017 | -1301271.4017
| 416 | 04. Receptacle WORK | [19 empty] | 0
| 417 | ELECTRICAL METALLIC TUBING (EMT) | 3/4" SET SCREW | LF | 1500 | 0.85 | 6.18 |  | 7.03 | 10545 |  | 0 |  | 0 | 0 | 0 | 0% | 1500 | 10545 |  | 0 | 0
| 418 | CONDUIT SUPPORT SYSTEM | 3/4" | SET | 300 | 5.36 | 25.24 |  | 30.6 | 9180 |  | 0 |  | 0 | 0 | 0 | 0% | 300 | 9180 |  | 0 | 0
| 419 | SINGLE CONDUCTOR (THHN/THWN) - STRANDED | AWG#12 | LF | 1350 | 0.28 | 1.27 |  | 1.55 | 2092.5 |  | 0 |  | 0 | 0 | 0 | 0% | 1350 | 2092.5 |  | 0 | 0
| 420 | Multi Conductor (THHN/THWN) - Stranded | (3PH) AWG#10 | LF | 400 | 1.11 | 2.16 |  | 3.27 | 1308 |  | 0 |  | 0 | 0 | 0 | 0% | 400 | 1308 |  | 0 | 0
| 421 | Multi Conductor (THHN/THWN) - Stranded | (3PH) AWG#12 | LF | 400 | 0.89 | 1.92 |  | 2.81 | 1124 |  | 0 |  | 0 | 0 | 0 | 0% | 400 | 1124 |  | 0 | 0
| 422 | MC(FLEXIBLE ALUMIUM CONDUIT) CABLE | (3PH) AWG#10 | LF | 600 | 1.7 | 2.84 |  | 4.54 | 2724 |  | 0 |  | 0 | 0 | 0 | 0% | 600 | 2724 |  | 0 | 0
| 423 | MC(FLEXIBLE ALUMIUM CONDUIT) CABLE | (3PH) AWG#12 | LF | 600 | 1.39 | 2.54 |  | 3.93 | 2358 |  | 0 |  | 0 | 0 | 0 | 0% | 600 | 2358 |  | 0 | 0
| 424 | MC CABLE HANGER CLAMP | 14-2 TO 10-3 MC | EA | 240 | 3.2 | 17.78 |  | 20.98 | 5035.2 |  | 0 |  | 0 | 0 | 0 | 0% | 240 | 5035.2 |  | 0 | 0
| 425 | Metal Clad Cable(M/C) Fitting | Busing,Wirng nuts,Wire & etc | EA | 90 | 4.28 | 15.46 |  | 19.74 | 1776.6 |  | 0 |  | 0 | 0 | 0 | 0% | 90 | 1776.6 |  | 0 | 0
| 426 | JUNCTION BOX, NEMA-1 | 4"W x 4"H x 2-1/4"D | EA | 80 | 9.66 | 44.78 |  | 54.44 | 4355.2 |  | 0 |  | 0 | 0 | 0 | 0% | 80 | 4355.2 |  | 0 | 0
| 427 | CONNECTION AND TERMINATION | AWG#10 COMPRESSION TYPE | EA | 180 | 3.74 | 14.88 |  | 18.62 | 3351.6 |  | 0 |  | 0 | 0 | 0 | 0% | 180 | 3351.6 |  | 0 | 0
| 428 | CONNECTION AND TERMINATION | AWG#12 COMPRESSION TYPE | EA | 180 | 2.14 | 11.45 |  | 13.59 | 2446.2 |  | 0 |  | 0 | 0 | 0 | 0% | 180 | 2446.2 |  | 0 | 0
| 429 | Receptacle | 20A 120V Duplex | EA | 15 | 15 | 52.84 |  | 67.84 | 1017.6 |  | 0 |  | 0 | 0 | 0 | 0% | 15 | 1017.6 |  | 0 | 0
| 430 | Receptacle | 20A 120V Duplex, GFCI (Weatherproof) | EA | 15 | 34.86 | 60.86 |  | 95.72 | 1435.8 |  | 0 |  | 0 | 0 | 0 | 0% | 15 | 1435.8 |  | 0 | 0
| 431 | Receptacle Cover | Duplex, Weatherproof | EA | 2 | 15 | 22.96 |  | 37.96 | 75.92 |  | 0 |  | 0 | 0 | 0 | 0% | 2 | 75.92 |  | 0 | 0
| 432 | [19 empty] | 0 | 0
| 433 | [ Sub Total ] | [7 empty] | 48825.62 |  | 0 |  | 0 |  | 0 | 0% |  | 48825.62 |  | 0 | 0
| 434 | 05. INCIDENTAL EXPENSE | [19 empty] | 0
| 435 | SHOP Drawing & Permit | UL INSPECTION W/CERTIFICATION, LV TES, Start UP & ETC | L/S | 1 | 0 | 29452.91 |  | 29452.91 | 29452.91 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 29452.91
| 436 | Waste Disposal |  | L/S | 1 | 0 | 7965.88 |  | 7965.88 | 7965.88 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 7965.88
| 437 | Gravel #57 | Ton | Ton | 10 | 24.13 | 51.37 |  | 75.5 | 755 |  | 0 |  | 0 | 0 | 0 | 0% | 10 | 755
| 438 | Lawn Recover | Sqft | FT2 | 25 | 0.79 | 3.98 |  | 4.77 | 119.25 |  | 0 |  | 0 | 0 | 0 | 0% | 25 | 119.25
| 439 | Demolition & Relocation | HZD-6H, Lighting , HZD-6L,TR-HZD-6 etc. | L/S | 1 | 804.67 | 21196.92 |  | 22001.59 | 22001.59 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 22001.59
| 440 | Circuit Route Change | Existed Circuits to New Panel | L/S | 1 | 1072.89 | 12613.28 |  | 13686.17 | 13686.17 |  | 0 |  | 0 | 0 | 0 | 0% | 1 | 13686.17
| 441 | [19 empty] | 0 | 0
| 442 | [ Sub Total ] | [7 empty] | 73980.8 |  | 0 |  | 0 |  | 0 | 0% |  | 73980.8 |  | 148602.7835 | -148602.7835
| 443 | 06. FIRE ALARM SYSTEM | [19 empty] | 0
| 444 | Fire Alarm System | UL INSPECTION W/CERTIFICATION, LV TES, Start UP & ETC | FT2 | 4923 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0% | 4923 | 0 |  | 0 | 0
| 445 | [19 empty] | 0 | 0
| 446 | [ Sub Total ] | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 0% |  | 0 |  | 2913982.4308 | -2913982.4308